PJ303: Integrating Microsoft Project with Microsoft Access

Cover Screen

Presented by:	Johnny Johnson

Mr. Johnson is a technical consultant for Micro-Frame Technologies, Inc. He has taught computer science at the U.S. Naval Academy and business management courses at community colleges. He has developed large-scale project management and database systems for the FAA, U.S. Air Force, Martin Marietta, as well as other government and commercial customers. He is a Microsoft Project Solutions Partner and Trainer.

Phone: (206) 598-5842

Fax: (206) 598-5843

CompuServe: 74415,1237

© 1995 Microsoft Corporation.

THESE MATERIALS ARE PROVIDED “AS-IS,” FOR INFORMATIONAL PURPOSES ONLY.

NEITHER MICROSOFT NOR ITS SUPPLIERS MAKES ANY WARRANTY, EXPRESS OR IMPLIED WITH RESPECT TO THE CONTENT OF THESE MATERIALS OR THE ACCURACY OF ANY INFORMATION CONTAINED HEREIN, INCLUDING, WITHOUT LIMITATION, THE IMPLIED WARRANTIES OF MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE. BECAUSE SOME STATES/JURISDICTIONS DO NOT ALLOW EXCLUSIONS OF IMPLIED WARRANTIES, THE ABOVE LIMITATION MAY NOT APPLY TO YOU.

NEITHER MICROSOFT NOR ITS SUPPLIERS SHALL HAVE ANY LIABILITY FOR ANY DAMAGES WHATSOEVER INCLUDING CONSEQUENTIAL INCIDENTAL, DIRECT, INDIRECT, SPECIAL, AND LOSS PROFITS. BECAUSE SOME STATES/JURISDICTIONS DO NOT ALLOW THE EXCLUSION OF CONSEQUENTIAL OR INCIDENTAL DAMAGES THE ABOVE LIMITATION MAY NOT APPLY TO YOU. IN ANY EVENT, MICROSOFT’S AND ITS SUPPLIERS’ ENTIRE LIABILITY IN ANY MANNER ARISING OUT OF THESE MATERIALS, WHETHER BY TORT, CONTRACT, OR OTHERWISE SHALL NOT EXCEED THE SUGGESTED RETAIL PRICE OF THESE MATERIALS.

more

Microsoft Project 4.0 and Microsoft Access 2.0

more

Why Integrate Project Management Data with a Relational Database Management System?

Since the CPM schedule and resource data is only part of the management problem, I almost always find that data from traditional project management systems needs to be integrated with accounting, text documents, pictures, charts, and other organizational data. This is where I find that a relational database is needed. In some cases, this database is actually part of the project management software and totally integrated. These software packages, however, cost thousands of dollars, are very specialized, and require many $$ in custom programming to make turnkey systems, and generally are very expensive to maintain. The question we need to ask is, how can we give Microsoft® Project project planning software, Microsoft Office office suite, and Microsoft Windows® operating system–based tools that same level of integration? The glue that we need to bind this type of development is a good relational database and a simple programming environment. Microsoft has provided these in Microsoft Access database management system, Microsoft FoxPro® database management system, Microsoft Visual Basic® programming system, and Microsoft Visual Basic for Applications. Using these tools, we can create an integrated, distributed project management environment.

In project management integration, I prefer an Integrated Information System (IIS) approach, where I see the relational database system as the central point of access to the data and to other software because:

	Schedule data is only a part of the total management problem.

	Many people have access to the project management data without having to understand the complexities of project management software.

	One can use the database to import, export, process, or report on data.

	One can query external databases directly or “lookup” data.

	One can “launch” other products using an “application execute” or “OLE” approach.

	One can use “DDE” or “OLE” to maintain a “real-time” update between products.

	One can build a consistent user interface in the database product.

	One has better control of data validation in the DBMS.

I would like to concentrate this discussion on using Microsoft Access as the example database, knowing that there are other products that could also do the job. I particularly like to use Microsoft Access because of its ability to “access” other databases without importing data but by attaching to the database files via ODBC and using their data. We can still maintain any current system by using the original database language then using Microsoft Access to create reports or even update data across several dissimilar databases. Of particular interest is Microsoft Access’s ability to have a data field type that is an OLE object. Additionally, we can liberally use Visual Basic 3.0 and Visual Basic for Applications to create functions, forms, and add functionality.

more

Organizational Implications of a Database of Project Management Data

I would like to discuss the organizational and philosophical implications of integrating project management data with database systems.

The first questions we should answer are:

1.	Who needs to see which data elements?

Engineers at the detail level need more information than the supervisor or the supervisor’s manager. This is always a hard question to answer because it involves organizational attitudes about “micro” management or to what level do we roll up data at each management level. Generally speaking, the less data depicted the better. You can always get detail data when needed. If all management needs to know “When will it be ready?”, then just let them see completion dates (scheduled finish, early finish, or late finish data elements).

2.	How often is data updated? By whom? Do we need “real-time” or periodic updated?

Many times I have seen organizations that say they must have “real-time” updates, yet they only update data weekly and report on it monthly. The costs in hardware, development, and security may be an unnecessary expense. The entire system development approach depends on how this question is answered.

3.	How often are reports due?

What is the reporting cycle or when do reports have to be presented? Are they due daily, weekly, bi-monthly, monthly?

4.	What form do the data elements need to be viewed?

What form (graphical, bar chart, tabular, Gantt, Pert, and so on) is the best way to display the data? Project schedules may make more sense displayed as Gantt charts but at times a tabular list of finish dates may be more appropriate.

5.	To what level of detail do I need to manage? (Managing to Your Threshold of Pain)

If I collect schedule data by the minute, that means my schedule could change every minute, and would require status to be updated every minute or my schedule would be wrong. This is appropriate if you are launching a space shuttle, but for most companies, trying to plan to that level generally not necessary. It has been my experience, that very little takes less than four hours, considering telephone calls, coffee, impromptu meetings, and other interruptions. I try to factor these considerations in when I estimate durations of work. In some instances, if work durations are very critical, some form of risk analysis could be used to define worst, best, and most likely duration’s for a piece of work. Remember, data systems are supposed to save time but they don’t guarantee that you will. If you find engineers spending more time entering or manipulating data, they are most likely spending less time on engineering, which is their primary function.

6.	What data elements need to viewed together and where do those elements currently exist (in other systems, on paper, in someone’s head)?

Is there significant data existing somewhere else? Can I attach or import that data? If I can, which data elements do I need? The trick here is to reduce data redundancy, keep data integrity, and keep down development costs. This is where Microsoft Access’s ability to attach to data is especially useful.

more

Specific Approaches to Integrating Microsoft Project Data with Microsoft Access Data

more

Microsoft Project

	Use Microsoft Project to create schedules and produce graphical reports at the detailed planner or working level.

Export “rolled-up” summary data to Microsoft Access for management reporting. Most managers don’t care how schedule data was obtained, they just want to know when we will finish and how much will it cost. In other words, can we complete “on time” and “on budget” or are there legitimate delays or cost overruns? “Rolling-up” data from Microsoft Project to Microsoft Access isolates the detail from the managers and allows them to concentrate on only the data needed for management decision making and reporting, thus avoiding information overload. By using Microsoft Access, many people may have access to the data without having to understand the complexities of Microsoft Project. How current this data needs to be is a function of the reporting and updating cycles.

	Use Microsoft Project to export detailed data to Microsoft Access for integrated relational reports.

The hardest reports to do in Microsoft Project are those that require a “one-to-many” relationship, such as resources related to tasks and grouped by task. Microsoft Project 4.0 allows a direct export of all of its data to a Microsoft Access database including Task, Resource Pool, Resource Assignment, and Project Header Information. Four tables are created in Microsoft Access, allowing for easy linking of one-to-many data elements.

You may copy as many projects as you want into the Microsoft Access database, as each project maintains a unique “key.” Project may also load projects from this Microsoft Access project database. This capability gives rise to several interesting implementations which I will discuss later.

	Use Microsoft Project to produce graphical reports from Microsoft Access data.

In some cases we could send manually entered schedule dates from Microsoft Access to Microsoft Project to produce simple Gantt bar charts. This is especially useful for schedule data that requires no “logic” (dependencies) and we could simply send the task name and the start and end dates to produce bar charts.

more

Microsoft Access

	Use Microsoft Access to produce detailed management reports about schedule or resource usage.

Use Microsoft Access for integrated tabular and graphical reports. Examples of this could include: integrating resource schedule data with accounting data, time sheets, or for forecasting. We could also use this method for trend analysis or saving historical schedule data for later analysis or regression. Another report might be forecast versus actual spending curves.

	Use Microsoft Access to collect changes in schedule and status.

Many users can update status or changes, such as actual start and complete dates, and percent complete, in the multiuser database. That data can then update schedule data in Microsoft Project.

	“Look-Up” the schedule from the Microsoft Access database.

In this approach, you could leave the schedule data in Microsoft Project, then through OLE or an Application Execute command in a macro start Microsoft Project with the corresponding schedule for the project you are currently viewing in the Microsoft Access database.

more

Microsoft Project to/from Microsoft Access Using the 'Save to Database' Feature

With Microsoft Project 4.0, you may save a project to a Microsoft Access database directly. You may have it automatically create a “new” database with the correct “project” structure or append or update a previously created “project” database. The Microsoft Project data transferred is captured in four Microsoft Access tables including: Tasks, Assignments, Resources (Pool), and the Project Header data such as Project Name, Manager, Company, and so on. Basically, all data needed for a project is transferred.

more

The PROJ2ACC.DLL & PROJ2ACC.INI

When you install Microsoft Project 4.0, you can optionally install the Save to Database utility. In addition to installing the proj2acc.dll, a proj2acc.ini is created in your Windows directory. The proj2acc.ini file contains startup information when selecting Save to Database or Open from Database functions in Microsoft Project 4.0.

PROJ2ACC.INI

[Project Converter 4.0]

SystemDB=No  (points to Microsoft Access System database - needed 				if database security is used)

LocalSave=yes (default=no, whether to save local copy of project

when opened from database)

DeleteLocalFiles=yes (default=no, delete local file after a 					successful database update)

LocalSavePath=E:\PROJ40 (where to save locally)

LastDB=C:\MFTITE95\MFTITE95.MDB

DefaultDB=no (if this path exixts, the database name select 					dialog box is skipped)

AutoOpenLastDB=no (whether or not to automatically use the last 				database when displaying the Open from Database 				dialog)

more

Details about the Save to Database Utility

The first time you save a project using the Save to Database utility, the “DLL” and associated Visual Basic for Applications code write out the entire project as a temporary MPX formatted file. Next, you are prompted for a database name to which to save the data. If the database doesn’t exist, a database “container and data structure” by that name is created and the data is loaded. If the database already exists, then the project data is added. If that project already exists in the database, it will delete the previous project data and replace it with the new data. (It doesn’t merge data, it is always a total overwrite) The temporary MPX file is deleted and control is returned to the Microsoft Project 4.0 user. Once you have saved a project to a database the first time, the project remembers where it was saved. The next time you save the project using the Save to Database utility, it will automatically be saved to the database where it was last saved. Each project file holds this intelligence in the Text 1-4 fields of Task 0 (the Project Summary task).

Illustration

Text1: holds the Microsoft Access ProjectKey field which is a unique date-time stamp.

Text2: holds the name of the database where the project was last saved.

Text3: holds the last saved date.

Text4: holds the project name.

more

Limitations to the Save to Database Utility

	Can open or save only entire projects, not filtered or parts of projects.

	Cannot save sub-projects with the project itself. Sub-projects must be saved separately.

	Because the utility uses the MPX interface format, very large projects take a while to read and write.

	If you make changes to your project in the database, then open the project from the database, you may get errors and lose data because of Microsoft Project 4.0’s validation upon reading the MPX file. This occurs when making changes in actual values to dates, work or cost. If the actual exceeds the scheduled, you will get a read error in Microsoft Project 4.0. A work-around is to ensure that you do in the database what Microsoft Project 4.0 would do. When you enter actuals greater than or equal to the scheduled data, set the scheduled data equal to the actual.

more

The Microsoft Access 'Project Database'

The specifics of the Microsoft Access “project” database structure allow for the user to relate all data.

1.	All table records are “keyed” to a unique Project Key. A sample of the project table data structure definition follows:

Illustration

2.	Relational queries are the basis of Microsoft Project data in the Microsoft Access database.

Relational reports can be produced by linking the Microsoft Project “key” fields such as “ID” or “UniqueID,” along with the Project Key field. The following Microsoft Access query typifies what one would need for a “one-to-many-to-many” type of relationship. Each project has many tasks, which in turn have many resources. It is important to note that the project key is very important when grouping tasks and resources by project. In the example query that follows, you will see that without the “ProjectKey,” one could not tell which tasks or resources belong to which project.

Illustration

Illustration

3.	Cross-project (multiple) project analysis and reporting is possible in the relational environment. The picture below shows a very simple report using the previous query. The report relates Resources to Tasks to Projects.

Illustration

Illustration

4.	Reports can be created using other database data in Microsoft Access or by attaching to other ODBC databases for “joined” reporting.

5.	You can update data in Microsoft Access, then send data back to Microsoft Project 4.0 for recalculation. (This must be done carefully when changing the “actual” values. For example, Scheduled data must be set to Actual data when it is equal or exceeds Scheduled values.)

6.	While the project data is in the database, you have complete multiuser access to the project schedules and can create a system in Microsoft Access including security, forms, reports, and so on.

more

Processing 'Projects' Stored in Microsoft Access  Database

In Microsoft Project 4.0, you may open projects directly from the Microsoft Access Project database. Since all project data is saved to the database, you can reopen a project at any time; you don’t need to save the .MPP file unless you need to for local reasons. After Microsoft Project 4.0 recalculates the data, changes the logic, and so on, the project can be “saved” back to the original database, thus updating the “master” Project database.

more

Possible Integration Scenarios

There are two scenarios that come immediately to mind.

1.	The first is to store all project data only in Microsoft Access. After Microsoft Project 4.0 creates schedules, save all projects into the Project database and do not save or maintain the *.MPP files.

2.	The second way is to store Microsoft Project 4.0 data in the Microsoft Access “project” database ONLY for reporting purposes. All changes are maintained in the Microsoft Project 4.0 files (*.MPP”) locally. This data is then saved periodically to the “project” database.

Both of these scenarios assume that everyone involved in updating a specific schedule are using the same calendar; otherwise the calculations of schedule dates will vary.

As in all distributed multiuser implementations, contention is an issue. Who has a copy of the project from the database on a local machine? If more than one person has a copy, there is a possibility of one person overwriting anther person’s data in the database. These issues can be taken care of through policy, security, or an automated “check-out” procedure built into the Microsoft Access system.

more

The TechEd 95 Demo Database

The demo database, MFTITE95.MDB contains all of the demos shown and many sample forms, queries, and reports. Once you start Microsoft Access 2.0 and open the MFTITE95.MDB, go to the forms tab on the database menu and open “frmDemoMainMenu” which brings up a form that allows you to easily explore the demo forms, queries, and reports. The demo database is intended to show you ways to properly link tables, make complex queries, design simple forms and produce complex reports across all of the projects in the database. The power of this approach is that it requires virtually no programming to create. Obviously, very sophisticated applications can be produced by using Microsoft Access Basic and macros.

Illustration

Illustration

more

Finding Schedule Data Across All Projects

The purpose of the Project Summary form is to demonstrate creating a main and subform and linking them together with the ProjectKey, which is created when a Microsoft Project 4.0 project is saved to the database, using the “Save to Database” utility. The main form browses the Project table, which has one summary record for each project in the database. The subform, which is linked by ProjectKey, lists all tasks associated with the current Project selected in the main form. Using a Main/Subform metaphor is natural because of the one-to-many relationships that occur in project management models. Users may quickly browse the schedule data across all projects and need not go back to Microsoft Project 4.0 to view this data. Remember, the advantage of using Microsoft Access and Microsoft Project together is that everyone can view project management data without having to be a project manager or have training in project management.

Illustration

more

Selecting Like Tasks Across All Projects

There are times when you want to compare the same task across all projects. The Select Specific Task form demonstrates selecting a unique task name from a list box, then displaying all matching tasks across all projects. In this case the main form is based on a list of unique tasks. When you select a task, the subform, which is linked by the Task Name to the list box control name (the selected task), the subform updates the data to match the selected task.

Illustration

Illustration

more

Finding What Resources Are Assigned to a Specific Task

To answer the question, “Who is working on a specific task on a specific project?” use the Show Resources Assigned to Task form. Again this form uses a main/subform construct linking this time on both ProjectKey and Task Name to select the subform data. Although it might be faster to link on TaskID, there is no guarantee that the same task name will have the same TaskID across several projects. In Microsoft Project 4.0, it is very difficult to ensure the same TaskID across like work. If this is necessary, it might be better to create a standardized coding scheme and use one of the user text fields (Text1-Text10) and assign it there.

Illustration

n this case the values returned by the list box controls are used to link to the subform. SelectedTask and SelectedProject are the names of the list box controls and assume the value returned for the bound column of the combo box.

Illustration

more

What Tasks Are Assigned to a Specific Resource?

Probably the most complex query you can make, using the four basic tables in the Project database, is to find out which resources are assigned to which tasks on which projects. It is the one-to-many-to-many that makes this query interesting. The demo form allows you to select a unique resource name then link to the subform query by resource name. You cannot use resource IDs because you cannot guarantee that the resource pool across all projects is consistent. Each project, when saved to the database, gets its own copy of the resource table (pool). There are ways to maintain a common pool but they require that you set up the system and procedures up front. In other words, set up and ensure that everyone uses the common resource pool from the outset.

Illustration

more

Demo Reports

The demo reports included in the database demonstrate how to create the underlying queries and group them correctly to get resource and task data. The Resources by Task report groups on Project.Name and Task.Name and is sorted by early task start date as follows:

Illustration

Illustration

Totaling in a report can be done in the footer of the group you are totaling. In this case, I totaled the resource cost for each task by creating a text box with its control source equal to =Sum([Cost]) in the tasks footer. To get the total for the project, just duplicate the text box in the project footer and the total of all task costs gets added there.

Illustration

Illustration

more

The Tasks Assigned to a Specific Resource Report

This report is less complex than the last report because it only groups on resource name.

Illustration

more

The Classic 'Look Ahead' Report

The “Soon to Come Due 30/60” report uses a calculated field in the query to make the report group on tasks due from today plus 30 days and tasks due 30 to 60 days from now. This technique makes “look ahead” reports very easy. First, the Due3060 query limits all tasks to those scheduled to finish from “Now” until 60 days from now. To do this, simply enter the Finish field’s criteria as:

>Now() And <Now()+60

Illustration

The trick in this query is to create a calculated field called “Due” then make it equal to a Boolean expression as follows select Shift-F2 to zoom in so that it is easier to type in the expression. Basically, if a finish date falls between now and 30 days from now, Due is equal to “30” and if the finish falls between 30 to 60 days from now, Due is equal to “30 to 60.” Now the report groups on “Due” and sorts by ascending finish date.

Illustration

Illustration

Illustration

more

Conclusion

This presentation shows that by using both Microsoft Project 4.0 and Microsoft Access 2.0 together, one can not only create integrated applications but also make project management data available to a broad base of users without the overhead of providing project management training to those who need only view the data. Additionally, I hope you can see the advantages from both a system and organizational perspective of using Microsoft Project 4.0 in large-scale implementations.