E A S Y  P R O J E C T(tm)

USER MANUAL

Version 4.05

A Project Management and Tracking System

for the I.B.M. and Compatible Personal Computers

(c)Copyright 1987,1988,1989,1990,1991,1992 Parcell Software

All Rights Reserved

Parcell Software

P.O. Box 165

Geneva, Il  60134

U.S.A.

(c)Copyright 1987,1988,1989,1990,1991,1992  Parcell Software

All Rights Reserved Worldwide

Printed in the United States of America

Parcell Software

P.O. Box 165

Geneva, Il  60134  U.S.A.

Voice:   (708) 232-6328   (9:00 a.m. - 5:00 p.m. Central Time)

BBS/FAX: (708) 232-6339  Feel free to use for technical support

CompuServe:  72250,1356

Technical Support:  (900) 884-3578  (8:00 a.m. - 5:00 p.m. Central Time)

$2.00 per minute, first 18 seconds are free

Trademarks

Easy Project is a trademark of Parcell Software

I.B.M. is a registered trademark of the I.B.M Corporation.

dBASE is a registered trademark of Ashton-Tate, Inc.

License Agreement

Easy Project is a Shareware program.  It is not free.

Easy Project is copyrighted software owned by Parcell Software. Continued use requires a

registration fee of $59.00. Registration covers use on one PC only.  Multiple copies of Easy Project

must be purchased for use on multiple PC's.  Quantity discounts and site licenses are available.

All licensed users receive:

�  Latest version of Easy Project with Shareware screen disabled

�  User Manual

�  Notification of updates

�  Special BBS access

You are encouraged to copy and share this program with other users. When sharing this program,

all files and documentation must be distributed without any alteration.  No fee can be charged for

any copying or distribution except for a nominal fee to defray expenses.  Please consult the

VENDOR.DOC file for vendor distribution requirements.

Hardware Requirements

I.B.M. PC/XT/AT/PS2 or 100% Compatible with at least 512K RAM and any type monitor.  A hard

disk is strongly recommended.

DISCLAIMER OF ALL WARRANITES AND LIABILITY

PARCELL SOFTWARE SPECIFICALLY DISCLAIMS ANY WARRANTY, EITHER EXPRESSED OR

IMPLIED, INCLUDING BUT NOT LIMITED TO THE IMPLIED WARRANTIES OF MERCHANTABILITY

AND FITNESS FOR A PARTICULAR USE. THIS SOFTWRARE IS LICENSED AS 'AS-IS'.

IN NO EVENT SHALL PARCELL SOFTWARE BE LIABLE FOR ANY SPECIAL, CONSEQUENTIAL, OR

OTHER DAMAGES, INCLUDING LOSS OF PROFIT ARISING OUT OF THE USE OF THIS PROGRAM.

E A S Y  P R O J E C T (tm)

Introduction

Easy Project is a tool to assist anyone who manages projects.

Easy Project encourages the manager to define a project into a

series of phases and tasks.  Easy Project facilitates the

planning, scheduling and tracking of all types of projects. The

manager plans the activities or tasks in a top/down outline

fashion.  The Gantt chart displays the project graphically by

using time bars which span the time period of each task.  The

extensive reporting module helps document the status of the

project.

Easy Project features:

�  The ability to create projects with 2000 tasks

�  Gantt charts detailing planned vs. actual progress

�  Automatic scheduling

�  Extensive reporting

�  Context sensitive HELP

�  dBASE file compatibility

A sample project is provided to assist in using Easy Project.

Use the project number of 'EASY' (all caps) to access the sample

project data.

<<MAIN MENU SCREEN>>

System Software Requirements

For the purpose of this documentation, it is assumed the user has

a working knowledge of the DOS operating system.  The user should

be able to copy and backup files, create directories and edit

text files.  Please consult your DOS manual with questions

regarding any of those functions.

CONFIG.SYS File (A sample is included)

A CONFIG.SYS file must be in the root directory of your hard

disk or on your DOS system floppy.  This file must contain

the following two records:

BUFFERS = 18

FILES = 30

These values are minimum values. Consult your DOS manual for

further information regarding the CONFIG.SYS file.

To activate any changes made to the CONFIG.SYS file, reboot

the PC!

First Time Installation

Hard Drive

1.  Make a backup copy of the Easy Project master disk.

2.  Place your backup copy in floppy drive and type:

INSTALL <enter>

This installation procedure will prompt you for the drive

and sub-directory destination for the Easy Project files.

We recommend that Easy Project be installed in its own

directory (i.e. \EP40).

Upgrading From Prior Versions

To upgrade from a 3.X version, follow this procedure:

1.  Backup ALL present files

2.  Install Easy Project using the above procedure.  Be sure

to install the new version in a directory different than

the 3.X version.

3.  Start Easy Project and go to the Utilities Menu

4.  Choose the Convert 3.X file option

5.  Choose Configure System and update accordingly

Starting Easy Project

From the \EP40 (or the directory where you installed the system):

Type EP <enter>

Configuring Easy Project

The first time you execute Easy Project, choose the Utilities

option from the Main Menu.  From this menu, choose Configure

System and then Configure Printer and update accordingly.

Keyboard Control

On most Easy Project data entry screens, the cursor is controlled

in the following fashion:

Key                    Result

<��       Proceeds to the next field.  When pressed while

the cursor is in the last field of a screen, all

data will be saved.

PgDn      Exits the screen saving all changes.

Esc       Exits the screen without saving any changes.

Moves cursor to previous field.

Moves cursor to next field.

Moves cursor backward.

Moves cursor forward.

Ctrl End     Moves cursor to last field on data entry screen

F2        Displays program license and prints registration

form.

F5        Deletes current record while in Resource or Task

Parameter screens.

F8        Edits a task from the Gantt display.

F9        Scrolls Gantt chart into the past.

F10       Scrolls Gantt chart into the future.

Need HELP?

At any time, on-line help is available by pressing "F1".  Easy

Project will recognize what field or menu the request came from,

and then display the appropriate text.  Three fields will provide

additional HELP when the F1 key is pressed:

Project Number:  Lists all active projects on file.

Task Number:  Lists all tasks for a particular project.

Resource:  Lists all resources for a particular project.

Main Menu

The Main Menu permits access to your projects.  The desired

function can be chosen using two methods:

1.  Use the left or right arrow key to highlight the desired

option and then press the <Enter> key

2.  Press the capitalized letter of the desired choice (i.e.

T=Task, O=repOrt)

The components of the Main Menu are:

Project

Create project numbers, project descriptions,

phase descriptions and define holidays

Resource

Maintain resource data

Task

Maintain task data

Browse

Edit tasks in a spreadsheet fashion

Schedule

Automatically schedule work plans

Gantt

Produce Gantt charts detailing planned vs. actual

project progress

repOrts

Generate reports including work plans, status

reports and project summary reports

Utilities

Configure system and provides utility project

handling

sYstem

Shell to DOS

Exit

Quit Easy Project

Using Easy Project - A Fast Start

Easy Project is designed for quick project creation.  After

spending a short time entering project data, Gantt charts and

reports can be produced.

Follow this procedure when creating a new project:

1.  Choose 'Project' from the Main Menu and enter a project

number, descriptions, phase descriptions and project

holidays.

2.  Choose 'Resource' from the Main Menu and enter resource

data for the project.  Resources will be identified by

assigning them a unique code.

3.  Choose 'Task' from the Main Menu to enter and maintain

tasks for the project. (See Notes On Entering Tasks)

4.  To have Easy Project calculate a project schedule,

choose 'Schedule' from the Main Menu. (See Notes on

Automatic Scheduling)

5.  At this point, Gantt charts and reports may be produced.

NOTE:  A sample project has already been established.  Use the

project number of 'EASY' (all caps) to view this project.

Maintaining an Existing Project

When initially starting the system, no project will be active.

To activate or retrieve a project, you will be prompted for the

project number the first time you try any Main Menu function. To

change projects, go to the 'Project' screen or any report screen.

F1 Key

Remember to make use of Easy Project's context sensitive HELP

screens.  The F1 key can be pressed while in any part of the

system to provide quick support.

Project Parameters

Easy Project has the ability to store data from several different

projects at one time.  Each of those projects may have different

base parameters.

Before entering task or resource data for a particular project,

certain parameters or criteria must be defined on the Project

Parameter screen.

<<PROJECT SCREEN>>

Project Number

Every project must have its own unique project number.  This

number is used to tell the system what project should be

retrieved.  This number can be composed of any combination

of characters or numbers (5 character maximum).

The project number field is case sensitive - meaning it is

important to enter upper and lower case characters exactly

as previously entered.

NOTE:  Pressing the F1 key while on the project number field

will provide a list of all active projects.

Project Name

Use this field for the name of the project.  This

description will appear on all screens and reports.

Project Description

To further describe a project, use these fields.  The data

entered here will print on all reports.

Phase Descriptions

For most projects, it is better to divide the project into

smaller, more manageable phases.  Sample phases are:

1.  Dig foundation

2.  Framing

3.  Install plumbing

4.  Install electrical

Easy Project permits 20 different phases to be defined for

one particular project.  The descriptions entered here will

appear on project summary reports.

Non-Schedule Days

Twelve different dates may be entered as non-schedule days.

These dates will be skipped by the system in scheduling.

This will be useful in scheduling holidays and vacations.

Weekends?

If Saturday and Sunday are to be skipped when scheduling,

enter a 'N'.

If weekends are to be included in scheduling, enter a 'Y'.

Schedule Networks/Phases Parallel?

If phases or networks are to be scheduled in parallel

(concurrently), enter a 'Y'.  If used, all phases will begin

on the project start date.

Project Start Date

Enter the start date of the project.

Project Narrative

While using the Project Parameter Screen, pressing F3 will

pop up a text editor.  This text editor can be used to write

a project narrative or for any other purpose.  Pressing the

F4 key will send the text to an ASCII disk file called

PROJECT.TXT.  This file can be imported into a word

processing program.  Pressing the F6 key will print the

text.

Resource Maintenance

Before tasks can be entered, resource information must be

established.  Resources may consist of staff (employees,

consultants, sub-contractors, etc.) or fixed type (materials,

capital expenses, etc.).

<<RESOURCE SCREEN>>

Code

Each resource must be assigned a unique identifier.  This

identifier could be a name, initials or an account code.

The identifier can be up to 6 characters and is

alphanumeric.

This field is also case sensitive - meaning it is important

to enter upper and lower case characters exactly as needed.

NOTE:  Pressing the F1 key while on the Resource Code field,

will display a list all resources assigned to this project.

Name

Enter the full name or description of the resource.

Rate

The charge rate for the resource. If a 'Fixed' type, enter

the total expense amount. (optional)

Type

Choose either Hourly, Daily, or Fixed.  A Fixed type could

be used for one time capital expenses.

Dept (Department)

Enter a department code for the resource.  This code

may be up to 3 characters and is alphanumeric.

NOTE:  This is an optional entry but is needed to produce

departmentalized reports.

Usage

Use to identify how many hours this resource works in one

day.  (not needed for Fixed types)

Example:    8 = 8 hours/day

4 = 4 hours/day (part time)

Source

An optional entry to further describe the resource.

Example:    EMP = Employee

CON = Consultant

Notes

An optional entry to be used for any purpose.

Task Parameters

Task definition is the heart of project management. Before

sitting down and entering task data, plan what logical order your

tasks will follow and if possible, divide your project into

phases. Once your data has been entered, refinement and

maintenance is easy.

<<TASK SCREEN>>

Task

Enter a two digit phase number plus four digit task number

for this task. Refer to 'Notes on Entering Tasks' for

creating task numbers.

Item

Each task can consist of numerous subordinate tasks or

items.  Enter an item number (01-99) in this field.

(optional)

Network

Large projects may have different phases running

concurrently.  Use this to designate which network or node

this task belongs to.  For most projects, use the phase

number. (The default value is the phase number)

Successor

Use this field to define task dependencies. This is composed

of the Phase+Task+Item number of the succeeding task.  If

the succeeding task can run concurrently, just let use the

default value.

Description

Enter the description for this task. This description will

appear on all reports and Gantt charts.

Milestone

Milestones reflect major project accomplishments.  If this

task is considered a milestone in the project, enter a 'Y'.

Resource

Enter the code for the resource assigned to this task.  A

maximum of four different resources may be assigned to a one

task.  All resources must be set up prior by entering data

on the Resource screen.  Pressing the F1 key here will list

all valid resources.

Est. Time (Estimated Time)

Enter the estimated time (hours or days) needed to complete

this task.  If the resource type was 'Fixed', enter '1'

here.

Time To-Date

Enter the actual time (hours or days) spent thus far working

on this task.

New Est (New Estimate)

As the project progresses, enter the revised estimated time

to complete this task.  If the task is on schedule, this

field need not be modified.

Planned Start/Stop

Enter the original or planned start and stop date for this

task.  This is the date that reflects what was intended for

the task and should not be modified during the project.

Actual Start/Stop

Enter the actual or projected start and stop date for this

task.  This date should reflect what date the task will end

in reality.

Fixed Date

Enter a 'Y' if the dates associated with this task should

not be changed for any reason.  This is useful for vacation

use or for meetings with set dates.

Status

This will designate the status for this task.  When

completed, use a 'C'.  Other uses could be 'A' for active or

'I' for in-progress.

Notes

To be used for any purpose necessary.

Entering Tasks

Every task number consists of the following elements:

Task Number  - 2 character phase number (01-20) plus

4 character task number (user defined)

Item Number  - 2 characters, user defined (optional)

Successor    - 8 characters, made up of (Phase + Task +

Item)

Remember, most reports are produced in task number order.

Using sequential task numbers such as 0001, 0002, etc.

within each phase is recommended.

'Item' is designated for use as a subordinate task.  This is

an optional entry but is useful in breaking down a large

main task.  Again, it's useful to use sequential item

numbers within each task number.

Sample Task Numbers

Task Field  =  01-0001

Item Field  =  01

Successor   =  01-0001-02

Example:  This task belongs to Phase 1, Task equals 0001 and

this is the first item for task 0001. Task/Item 01-0001-02

cannot start until this task is complete. 01-0001-02 is

placed in the 'Successor' field.

Task Field  = 01-0003

Item Field  = <blank>

Successor   = 01-0003

Example:  This task belongs to Phase 1, Task equals 0003 and

there are no subordinate items.  No other task is dependent

upon this task so the 'Successor' field defaults to itself.

Assigning Successors

If a task cannot begin until the previous task is complete,

enter the task number of the successor in the 'Successor'

field of the current task.

Example:  A phase has 4 tasks, 0001 through 0004.  Every

task is dependent upon the previous task.  The tasks should

be established as follows:

Task              Successor

01-0001            01-0002

01-0002            01-0003

01-0003            01-0004

01-0004            01-0004

If tasks can run concurrent with each other, set up the

tasks in this manner:

Task              Successor

01-0001            01-0002

01-0002            01-0002 --

01-0003            01-0003  | Concurrent

01-0004            01-0005 --    Tasks

01-0005            01-0005

In this example, tasks 0002, 0003 and 0004 all we be

scheduled at the same time after task 0001 is completed.

Task 0005 will be scheduled after task 0004 is completed.

When scheduling in this fashion, task 0004 should be the

task with the longest duration of all the concurrent tasks.

Automatic Schedule Maintenance

If a planned start or stop date is changed, for an existing

task, the automatic scheduler will be invoked (based on the

parameter setting in System Configuration) adjusting both

planned and actual start and stop dates for all succeeding

tasks. You will have the ability to override the proposed

dates. Likewise, if a current start or stop date is changed,

the automatic scheduler will be invoked to adjust current

dates only.

Marking Tasks Complete

For the purpose of the Project Status Report and the Gantt

chart, a status of 'C' denotes that a task is complete.  For

other purposes, any other code may be used.

Browse

The Browse function provides a facility to edit tasks in a

spreadsheet type format.  All the fields that appear on the Task

Parameter screen are found on the Browse screen.

Use the arrow keys to move around the screen.  To change a field,

move to the field and press the <Enter> key.  This will activate

the field and any change can be made.

The PgDn and PgUp keys will advance the screen one page at a

time.

To delete a task, press the <Del> or <Delete> key.  An asterisk

(*) will appear at the beginning of the task number to denote it

has been deleted.  When records have been deleted, a 'Rebuild'

will be conducted to maintain the integrity of all related files.

New records can not be added using the Browse screen.  All new

tasks must be added using the Task Parameter screen.

Automatic Schedule Generation

Easy Project will automatically calculate task start and stop

dates based on the estimated time assigned to each task.

To calculate dates, first choose 'Schedule' from the Main Menu.

Next, enter the project number followed by the project start

date.  The project start date should be the date the schedule may

begin.

There are two other options listed in the Schedule window:

�  If only the project critical path needs calculating and a

project schedule is not needed, enter a 'Y' for the 'Calc

Critical Path Only' option.

�  If the project is composed of phases running

concurrently, enter a 'Y' for this option.  This will cause

each phase to be scheduled using the project start date.

Schedule Screen Display

As the schedule generates, each task and the newly calculated

dates are displayed.  After the screen fills, you have the

ability to change or override the calculated date.  Pressing

<ESC> aborts the update process and the records will not be

updated.

Use the <ENTER> key to advance the cursor. The <PgDn> key will

accept all dates and advance to the next screen.

<< SCHEDULE SCREEN >>

Notes on Scheduling

1.  In the case of tasks which have more than one resource

assigned to it, the resource taking the greatest amount of

estimated time will be used in calculating the schedule.

2.  Any task which has a Fixed type resource will be ignored

for scheduling purposes.

3.  On the Resource Parameter screen, the Usage field should

reflect the total number of hours the resource works in one

day. Use this for both hourly and daily type resources.

4.  Weekends will be taken into consideration when

calculating the schedule based on the option chosen from the

Project Parameter screen.

5.  If a task was set up with the Fixed Date option set, the

fixed date will be used instead of the calculated date.

Gantt Chart

Easy Project's Gantt charts are designed to give a graphic

display of a projects planned vs. actual progress.

<<  GANTT SCREEN  >>

Two different types of charts may be produced:

1.  A chart displaying tasks for one particular phase in

task number order.

2.  A chart displaying the entire project with tasks grouped

by dependencies.

NOTE:  In order for a task to be displayed, it must have a

Planned Start Date and Planned Stop Date.

Format Options

The format of the Gantt chart can be altered in several

ways.  Options exist for displaying or not displaying

resource, status and critical path codes.  Also, either the

full task description or truncated descriptions with task

numbers can be chosen.  All options are set from the System

Configuration screen from the Utilities Menu.

Scale Options

Flexible Gantt scales can be chosen to insure the most

complete view of a project.  Each symbol on the chart can

represent from 1 to 6 days or 1 to 6 weeks.  For projects of

short duration, a scale in days is probably more

appropriate.

Output Options

Easy Project offers three output options for producing

Gantt charts:

1.  (D)isplay - The chart will be displayed on your

monitor.

2.  (P)rint - The chart will be routed to your printer.

By printing in a compressed format, a longer view will

be produced.

3.  (F)ile -  The chart will be written to a disk file

using the default file name of GANTT.PRN.  This is an

ASCII text file that may be printed through DOS or

another printing utility.  By using either a wide

carriage printer or a sideways printing utility, an

even longer view may be produced using this option.

Gantt Chart Symbols

�      Planned Date

�      Actual Date

*      Completed Task

M      Milestone

CRIT!  Critical Task

Task has start date prior to beginning of scale

+      Task has multiple resource assignments

Use of the F8 Key

The up and down arrow keys will move the highlight bar to

each task displayed.  To edit a  task, press the F8 key.

Pressing F8 will display the Task Parameter screen for the

task.  To return to the Gantt chart, just press the <ESC>

key.

Reports

Easy Project has an extensive reporting module.  Many helpful

reports may be instantly displayed, printed or written to a disk

file.  Most reports will print in a compressed format - thus

giving more detail than when displayed.

If the 'File' output option is chosen, the report will be written

to a disk file in an ASCII format.  This file can be imported

into almost any word processor for further editing and printing.

A plus sign next to a resource code indicates the task has

multiple resource assignments.  Check the Appendix for samples of

all reports.

Work Plan By Task

Produces a detailed work plan or schedule for a particular

phase in task number order. [prints compressed]

Work Plan By Resource

Produces a detailed work plan or schedule for the entire

project by resource assignment.  [prints compressed]

Work Plan Project Summary

Summarizes all phases of a project plan giving a concise

summary.

Work Plan Resource Summary

A departmentalized resource summary for a particular phase

or the entire project.

Project Status Report - Plan vs. Actual

A status report for the entire project detailing cost and

schedule variances.  [prints compressed]

Project Status Summary - Actual

Summarizes all project phases showing actual costs and

current schedule dates. [prints compressed]

Project Resource Summary - Actual

Produces departmental break down of actual costs by

individual resource.

Earned Value Report

A report detailing project cost accruals. [prints

compressed]

Resource List

A detailed list of all resources assigned to a particular

project.

Work Plan - All Projects

A detailed resource schedule using all active projects.

This report will be helpful in identifying resource

scheduling conflicts. [prints compressed]

Formatted Task List

Produces a formatted screen print of the Task Parameter

screen.

Utilities

The Utility Menu consists of functions that are used for

configuration, file conversions and file maintenance.

With any application, it is a good practice to backup all Easy

Project files on a regular basis. This will help in recovering

from any potential accidents or disasters.

Reindex All Files

Easy Project uses index files (.NTX) which permit fast data

retrieval.  These index files are not compatible with dBASE

.NDX files.  All files with the extension of .NTX should

never be deleted or altered. If file integrity is ever in

question, choose this option.

Delete (Pack) Marked Records

When task or resource data is deleted using the 'F5' key,

the records are marked for deletion but physically remain on

file.  These records are unavailable for normal use.  This

delete option  will physically delete all marked records.

Once this option is exercised, the marked records can no

longer be recovered.

Undelete (Recall) Records

This option will find all records that have been marked for

deletion (but not yet packed), and recall them again for

processing.

NOTE:  This option will recall all records from all projects

from all files regardless of project number.  Use this

option with caution.

Delete Project

This function will delete all tasks, resources and related

records for a project.

To use, first enter the project number to delete.  Next, you

will be prompted to verify the project number.  Answering

'N' will bypass any deletions.  If verified, records are

then marked for deletion.

Copy or Clone Project

A new project may have many of the same characteristics as

an established project.  This copy option will copy a

current project and duplicate all tasks and resources using

a new project number.  The old project remains intact

without any changes.

Copy or Clone Resources

This option will copy resources from one project and

duplicate them using a new project number.  The old project

remains intact without changes.

Rebuild Files

Easy Project database files (.DBF) are dBASE compatible and

can be used by many other applications.  Exporting files to

other software packages may provide useful for additional

reporting or analysis.

If files are updated outside of Easy Project, they must be

rebuilt.  This function will automatically rebuild index

files and all necessary data relations.

NOTE:  Exercise caution when updating Easy Project files

from outside applications.  Be sure to have recent backups

of all files as a safeguard.

Backup Files

On a regular and consistent basis, backups should be made of

Easy Project files.  This option will perform a DOS BACKUP

of all Easy Project files.  If using a two floppy system,

use drive A as the target or destination drive.

Restore Files

To restore files from a backup floppy, enter the source and

target designations.

If files are restored from a backup, be sure to use the

'Rebuild' option to maintain file integrity.

Configure System

This option sets the proper type of monitor for your system,

the proper destination for printer output, Gantt chart

display option and automatic scheduling options.  Also,

different date formats may be chosen as well as Gantt chart

and report formats.

Configure Printer

Easy Project supports many printers.  Find the number that

corresponds to your printer and enter the number at the

prompt.  If your printer is not listed, try either the

I.B.M. Graphics or an Epson printer. If you are having

unsatisfactory results with reports or the Gantt chart,

please contact Parcell Software for assistance.

Convert Version 3.X Files

Choose this option when upgrading from a 3.X version of Easy

Project.  Follow the instructions from the beginning of this

manual.

Conclusion

Easy Project is a dynamic system that is constantly being

enhanced.  Your suggestions and comments are greatly appreciated.

Our users are our greatest source of new ideas.

Thank you for adding Easy Project to your software library.

A P P E N D I X

�  Shareware Distribution

�  Sample Reports  (REGISTERED VERSION ONLY)

�  Index (REGISTERED VERSION ONLY)

SHAREWARE DISTRIBUTION

Parcell Software believes Shareware distribution constitutes a

viable, low cost alternative to many commercial programs.

Shareware's greatest strength lies in the ability to try software

before purchasing it.  We also believe that Shareware is maturing

as a distribution method and that its quality and functionality

is improving at a rapid rate.  This could only happen because

users, hopefully like yourself, are supporting Shareware products

by remitting their registrations.

We hope our product continues to be a productive element of your

system and we urge you to consider other Shareware products when

you decide to add software to your system.

Parcell Software is a member of the Association of Shareware

Professionals (ASP). The ASP has established stringent standards

for its memberm.  The ASP wants to insure the Shareware principle

works for you.  if you are unable to resolve a problem with an

ASP member (other than technical support), the ASP may be able

to help.  Please write the ASP Ombudsman at:

ASP

545 Grover Road

Muskegon, MI  49442-9427

CompuServe ID: 70007,3536

���������Ŀ

���������Ŀ     �             (tm)

�ĳ         �o    ������������������

�   ���������Ŀ �  Association of

�   �         ���  Shareware

���ĳ    o    �    Professionals

�����ĳ    �    ��������������������

�����������    MEMBER