ßßßßßßß    ßßßßßßß  ßßßßßßß  ßßßßßßßßßßß  ßßßßßßßßßßß
         ßßßßß      ßßßßß    ßßßßß   ßßßßßßßßßßß  ßßßßßßßßßßß
          ßßß        ßßß      ßßß       ßßßßß        ßßßßß
           ßßßßßßßßßßßß        ß         ßßß          ßßß
           ßßßßßßßßßßßß        ß          ß            ß
          ßßß        ßßß      ßßß        ßßß          ßßß
         ßßßßß      ßßßßß    ßßßßß      ßßßßß        ßßßßß
        ßßßßßßß    ßßßßßßß  ßßßßßßß    ßßßßßßß      ßßßßßßß
                          PERSONAL SOFTWARE



     SCHEDULE
     Shareware Version 1.2
     (C) Copyright 1984,88 Donald C. Hitt

     HITT Personal Software Company

     13 Rosalind Road
     Poughkeepsie, N.Y. 12601
     914-471-5354


     10-18-1988




















                                    SCHEDULE



     PROGRAM LICENSE AGREEMENT





     SCHEDULE Shareware version 1.2 is the property of

           HITT Personal Software Company
           13 Rosalind Road
           Poughkeepsie, New York 12601

     Using this program indicates your acceptance of the terms, conditions,
     and limitations for  the use of this program. If you do not agree with
     these conditions,  you should destroy the material immediately without
     attempting to use or copy it.



     LICENSE


     You may

     1.  Use the program for educational or personal purposes.

     2.  Copy the program for backup purposes in support of your use of the
         program.

     3.  Copy  the program for  another party  if the other party agrees to
         accept the terms and conditions of this agreement.

     4.  Terminate the  license at any time by  destroying  or transferring
         the program along with all copies.

     You must

     1.  Reproduce  and  include  the  copyright   notice  on  all  copies,
         modifications, or portions of this program.

     2.  Purchase the commercial version of the program from "HITT Personal
         Software Company"  if  you are using  the program  for  commercial
         applications.

     You understand that

     1.  There is no warranty.

     2.  There is no  oblication  on  the part of  "HITT  Personal Software
         Company" to provide  any level of service for the  free  Shareware
         version.

     3.  The program has  a limited capacity  designed  to  satisfy student
         homework problems.


     HITT Personal Software          Page ii





                                    SCHEDULE



     ABSTRACT





     SCHEDULE provides a system which allows task  and resource modeling to
     be  done independently from start/end  times. CPM and  PERT techniques
     are used to establish scheduling priorities.  The AON grid is  created
     automatically at the time the schedule is processed.

     A  rich assortment of  resource types are provided to allow  realistic
     modeling. The program works with resource limits to provide a schedule
     which  is  consistent  with  the  constraints  and  is  based  on  the
     priorities established by the requested completion times.

     The program control allows for background processing of the scheduling
     and  printing while providing keyboard and  display  services  in  the
     foreground.





































     HITT Personal Software         Page iii





                                    SCHEDULE



     PREFACE





     The  first  version  of  "SCHEDULE"  was  developed in the  1960's  to
     optimize the computer resources  of a  multiple  computer installation
     while prioritizing the schedule based  on requested completion  times.
     Those principles have  been  applied to this  system to provide a real
     time interactive resource scheduling system.

     The principles of  CRITICAL PATH SCHEDULING are used in an environment
     of  resource constraints.  This system generates  its  own matrix grid
     based on the requested end results.

     This system provides REAL TIME task coordination and dispatching while
     providing  INTERACTIVE  updating,  status  inquiries,  and   new   job
     scheduling.

     These features  allow the  program to be used effeciently  in a  broad
     range of applications.

     o   Project  managers   will   be   better  able  to  control  project
         interdependincys.

     o   Managers of small businesses  will  discover improvements in their
         ability to predict  when  a  job  will  be completed  as  well  as
         improvements in their resource utilization.

     o   Planners will find real answers to  difficult management questions
         concerning new resource assumptions or changes during the project.
























     HITT Personal Software          Page iv





                                    SCHEDULE



     USING THIS DOCUMENT


     The following is a general outline of the document.

     Chapters 1,  2, and 3 contains information  of general interest but is
     not required to use the program.

     Chapters 4,  and  5  is not required  if  you know your system has the
     required  features and you know how  to backup  your disks  using  DOS
     commands.

     Chapters 6, 7, 8, 9, and 10 describe the operation of the program.

     Chapters  11 defines the special types  of resources supported  by the
     program.  When you  start making  complex  task models this chapter is
     required reading.

     Chapter 12, 13,  and 14 describe three types of applications which you
     may wish to read. Also the STATION project is described in appendix B.

     Chapter 15 is  a collection  of  ideas on ways to use the program. You
     should review it to give yourself ideas.

     Chapter 16  is a list  of ways that others have had trouble. Review it
     if you think the  program is  acting strangely. It is required reading
     before getting serious.

     Chapter 17, and  18 is reference material which describes  the command
     language and the  program  exit codes.  This is useful when setting up
     automatic batch procedures.

     Appendix  A contains  an explanation  of  the  messages  which  may be
     produced by the program.

     Appendix B is the detailed data used with the STATION project.




















     HITT Personal Software          Page v





                                    SCHEDULE



     FEATURES


     Editing functions

     o   Full frame field editing
     o   Insert
     o   Delete
     o   Cursor control
     o   Field definition

     Overlapped operation

     o   Foreground entry/display
     o   Background processing
     o   Background (overlapped) printouts
     o   Continually active task display

     Multiple Job Mode

     o   Task definitions used for multiple jobs
     o   Resources shared across jobs
     o   Real time job additions/changes/control

     Calendar/time controls

     o   Calendars specified by resource
     o   Two time spans per day
     o   Calculations to the minute

     Five resource types

     o   Inventory (use once)
     o   Capital equipment (use repeatedly)
     o   Labor (restricted calendar/time)
     o   Job (associated with individual jobs)
     o   Buffer (can be added as well as deleted)

     Automatic network grid generation

     o   Based on task prerequisites.

     Built in Data Base Management

     o   Access by name
     o   Automatic additions and deletion
     o   ASCII format (editor compatible)

     Command Language

     o   Disk data used as keyboard input
     o   Direct display
     o   Conditional testing of screen data



     HITT Personal Software          Page vi





                                    SCHEDULE



     TABLE OF CONTENTS





     PROGRAM LICENSE AGREEMENT . . . . . . . . . . . . . . . . . . . . . II
     LICENSE . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . ii

     Abstract  . . . . . . . . . . . . . . . . . . . . . . . . . . . .  iii

     Preface . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . iv
     Using this document . . . . . . . . . . . . . . . . . . . . . . . .  v
     Features  . . . . . . . . . . . . . . . . . . . . . . . . . . . . . vi

     Chapter 1. About the Author . . . . . . . . . . . . . . . . . . . .  1

     Chapter 2. CPM and PERT . . . . . . . . . . . . . . . . . . . . . .  2
       A discussion of CPM and PERT  . . . . . . . . . . . . . . . . . .  2
         PERT, CPM, and MAP  . . . . . . . . . . . . . . . . . . . . . .  2
         Arrow and precedence methods  . . . . . . . . . . . . . . . . .  3
         Definitions for Project, Job, Task, and Activities  . . . . . .  3
         Time considerations . . . . . . . . . . . . . . . . . . . . . .  4
         Resource types  . . . . . . . . . . . . . . . . . . . . . . . .  4
         Decision making . . . . . . . . . . . . . . . . . . . . . . . .  5
       Summary . . . . . . . . . . . . . . . . . . . . . . . . . . . . .  6

     Chapter 3. Concepts of scheduling . . . . . . . . . . . . . . . . .  7

     Chapter 4. Minimum system requirements  . . . . . . . . . . . . . .  8

     Chapter 5. Preparing your diskette  . . . . . . . . . . . . . . . .  9

     Chapter 6. Operation description  . . . . . . . . . . . . . . . . . 10
     Function control keys . . . . . . . . . . . . . . . . . . . . . . . 10
     Display formats and control . . . . . . . . . . . . . . . . . . . . 11
     Edit and record selection conventions . . . . . . . . . . . . . . . 12
     Cursor controls . . . . . . . . . . . . . . . . . . . . . . . . . . 13

     Chapter 7. Creating the data base . . . . . . . . . . . . . . . . . 15
     Job description . . . . . . . . . . . . . . . . . . . . . . . . . . 15
     Task description  . . . . . . . . . . . . . . . . . . . . . . . . . 16
     Resource description  . . . . . . . . . . . . . . . . . . . . . . . 17
     Calendar definition . . . . . . . . . . . . . . . . . . . . . . . . 18

     Chapter 8. Starting and ending tasks  . . . . . . . . . . . . . . . 20

     Chapter 9. Interactive status displays  . . . . . . . . . . . . . . 21

     Chapter 10. Control frame . . . . . . . . . . . . . . . . . . . . . 23
     Printer output selections . . . . . . . . . . . . . . . . . . . . . 23
     Background processing control . . . . . . . . . . . . . . . . . . . 24
     Data Base Maintenance . . . . . . . . . . . . . . . . . . . . . . . 25



     HITT Personal Software         Page vii





                                    SCHEDULE




     Chapter 11. Special Resources . . . . . . . . . . . . . . . . . . . 27
     Inventory Resources . . . . . . . . . . . . . . . . . . . . . . . . 27
     Buffer Resources  . . . . . . . . . . . . . . . . . . . . . . . . . 27
     Job Resources . . . . . . . . . . . . . . . . . . . . . . . . . . . 28

     Chapter 12. Assignment tracking . . . . . . . . . . . . . . . . . . 30
     Job Definition  . . . . . . . . . . . . . . . . . . . . . . . . . . 31
     Task Definition . . . . . . . . . . . . . . . . . . . . . . . . . . 31
     Resource Definition . . . . . . . . . . . . . . . . . . . . . . . . 31
     Job file listings . . . . . . . . . . . . . . . . . . . . . . . . . 32
     Frame 10 controls . . . . . . . . . . . . . . . . . . . . . . . . . 32
     Summary . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . 32

     Chapter 13. Meeting Calendars . . . . . . . . . . . . . . . . . . . 33
     Job Description . . . . . . . . . . . . . . . . . . . . . . . . . . 33
     Task Description  . . . . . . . . . . . . . . . . . . . . . . . . . 33
     Resource Description  . . . . . . . . . . . . . . . . . . . . . . . 34
     Meeting calendar listings . . . . . . . . . . . . . . . . . . . . . 34
     Interactive meeting reminders . . . . . . . . . . . . . . . . . . . 34
     Automatic operation . . . . . . . . . . . . . . . . . . . . . . . . 34

     Chapter 14. Development project planning  . . . . . . . . . . . . . 36
     Detail level 1: . . . . . . . . . . . . . . . . . . . . . . . . . . 37
       JOB definition  . . . . . . . . . . . . . . . . . . . . . . . . . 37
       TASK definition . . . . . . . . . . . . . . . . . . . . . . . . . 37
       RESOURCE definition . . . . . . . . . . . . . . . . . . . . . . . 38
       The critical path . . . . . . . . . . . . . . . . . . . . . . . . 39
     Detail level 2  . . . . . . . . . . . . . . . . . . . . . . . . . . 39
       JOB definition  . . . . . . . . . . . . . . . . . . . . . . . . . 39
       TASK definition . . . . . . . . . . . . . . . . . . . . . . . . . 40
       RESOURCE definition . . . . . . . . . . . . . . . . . . . . . . . 40
       The critical path . . . . . . . . . . . . . . . . . . . . . . . . 40
     Detail level 3  . . . . . . . . . . . . . . . . . . . . . . . . . . 41
       JOB definition  . . . . . . . . . . . . . . . . . . . . . . . . . 41
       TASK definition . . . . . . . . . . . . . . . . . . . . . . . . . 41
       RESOURCE definition . . . . . . . . . . . . . . . . . . . . . . . 41
       The critical path . . . . . . . . . . . . . . . . . . . . . . . . 41
     Detail level 4  . . . . . . . . . . . . . . . . . . . . . . . . . . 42
       TASK descriptions . . . . . . . . . . . . . . . . . . . . . . . . 42
       RESOURCE descriptions . . . . . . . . . . . . . . . . . . . . . . 42
       CALENDAR descriptions . . . . . . . . . . . . . . . . . . . . . . 42
     Quality programs  . . . . . . . . . . . . . . . . . . . . . . . . . 42

     Chapter 15. Ideas for the expert  . . . . . . . . . . . . . . . . . 44
     Introduction to the expert section  . . . . . . . . . . . . . . . . 44
     Using SCHEDULE output as data for other programs or printers  . . . 44
     Building large similar files  . . . . . . . . . . . . . . . . . . . 45
     Creating calendars  . . . . . . . . . . . . . . . . . . . . . . . . 46
     Data base maintenance . . . . . . . . . . . . . . . . . . . . . . . 46
     Sorting the data base . . . . . . . . . . . . . . . . . . . . . . . 46
     Resolving multiple action required messages . . . . . . . . . . . . 47
         TASK "     " NOT FOUND FOR JOB "    " . . . . . . . . . . . . . 48
         CALENDAR " " NOT FOUND FOR RESOURCE " " . . . . . . . . . . . . 48


     HITT Personal Software         Page viii





                                    SCHEDULE



         RESOURCE "" IS NOT AVAILABLE FOR TASK ""  . . . . . . . . . . . 49
     Redefining the keyboard . . . . . . . . . . . . . . . . . . . . . . 49
     Header line printing  . . . . . . . . . . . . . . . . . . . . . . . 50

     Chapter 16. SCHEDULE TRAPS  . . . . . . . . . . . . . . . . . . . . 51
     Resource Names  . . . . . . . . . . . . . . . . . . . . . . . . . . 51
     HOURS/DAY field in the Task descriptions. . . . . . . . . . . . . . 51
     Creating GANTT files. . . . . . . . . . . . . . . . . . . . . . . . 51
     SCHEDULING late and CALENDAR NOT FOUND messages . . . . . . . . . . 52
     Editing the data base . . . . . . . . . . . . . . . . . . . . . . . 52

     Chapter 17.  Command File . . . . . . . . . . . . . . . . . . . . . 53
     Command definitions . . . . . . . . . . . . . . . . . . . . . . . . 53
     Additional control  . . . . . . . . . . . . . . . . . . . . . . . . 55

     Chapter 18. Program exit return codes to DOS  . . . . . . . . . . . 56

     Appendix A. Messages  . . . . . . . . . . . . . . . . . . . . . .  A-1

     Appendix B. SERVICE project environment and data base . . . . . .  B-1

     INDEX . . . . . . . . . . . . . . . . . . . . . . . . . . . .  INDEX-1


































     HITT Personal Software          Page ix





                                    SCHEDULE



     CHAPTER 1. ABOUT THE AUTHOR



     Donald C. Hitt  is a  Senior Engineer Manager for the IBM Corporation.
     He has been in the computer business for over 25 years with a majority
     of that  time in large system  design at IBM's Poughkeepsie,  New York
     Laboratory.

     While  Mr.  Hitt recognizes that IBM  holds the  rights  to all of its
     employee's  intellectual output, IBM has released  Mr.  Hitt to retain
     the rights  to this program. It was  developed independently  from his
     work at  IBM. IBM has reviewed this work, and has no objections to Mr.
     Hitt's marketing or distributing this program as submitted to them.

     Mr.   Hitt's  experience  with  development  projects  has  given  him
     knowledge  of management  techniques  and an appreciation  for project
     management systems. He feels  that PERT/CPM programs which cannot deal
     with constrained resources offer few benefits. The  program "SCHEDULE"
     was  created  because of the frustrations in trying  to use both  main
     frame and mini project management systems.

     According  to  Mr. Hitt, "SCHEDULE  does  what no other  program  even
     attempts to  do". He expects it  to set  new  precedents not  only  in
     scheduling technology but also in what he calls "expert friendliness".
     New users will spend extra time pressing the HELP key, with experience
     no keystrokes are wasted.

     The  company  "HITT  Personal  Software"  is  structured  to  be  cost
     effective. It operates out of the home of  Don and his wife Joan. Joan
     is a key contributor to this private business endeavor.




















     ----------------
     1  IBM is the trademark of International Business Machines
        Corporation.


     HITT Personal Software          Page 1





                                    SCHEDULE



     CHAPTER 2. CPM AND PERT



     A discussion of CPM and PERT


     The Critical Path Method and Program Evaluation and Review Technique

     Many text  books  are  available on the subject  of project management
     using  CPM and  PERT techniques. These techniques have received  mixed
     reviews partly  because the models they  produced did not  necessarily
     represent reality, and partly because  the effort required to use them
     can  be extensive  and untimely.  With the  introduction  of  the  IBM
     Personal Computer  an interactive, real time tool that overcomes these
     criticisms is now possible..

     This  document is not intended to teach CPM/PERT  techniques. A search
     of  the subject will reveal  numerous methods for optimizing resource,
     schedule, and  cost. These techniques do not provide a single solution
     to all  three parameters because  they remain independent or separated
     and  do not  converge. SCHEDULE  is  designed  to  help  you  optimize
     resource utilization  (indirectly cost), and  prioritize  according to
     the schedule.  In  addition  it provides a tracking/control tool which
     represents the project plan.

     The  remainder of this section is devoted  to  bridging  the text book
     definitions and SCHEDULE's  operation for  those who  are  interested.
     This understanding is not necessary to use the program.



     PERT, CPM, and MAP


     SCHEDULE is not a PERT program. It  uses single  task  times and these
     are considered  to be absolute. Normally  the  PLAN  of  a  project is
     considered to be  absolute but we all know it changes. When exceptions
     occur we  "change the plan"  so SCHEDULE is designed  to allow changes
     during the execution of the plan. Rescheduling is done at any time and
     actual start/end  of tasks are indicated to the program as  they occur
     so that it can track and adjust for changes.

     SCHEDULE is not a CPM program. It does not display to you the Critical
     Path or Slacks although it uses this information to establish resource
     priorities.  When  resources  are  committed  there  are  interlocking
     dependencies not  described by these parameters. It is possible that a
     delay in a low priority task (with lots  of  slack) could delay a high
     priority task because  it requires the  same  resource.  For a program
     like SCHEDULE, which is designed to operate with resource constraints,
     it is Resource Slack that is important.

     SCHEDULE is a MAP (Multiple-resource Allocation Procedure) program. It
     does not vary  resource  levels to maintain  a schedule  (it will  use


     HITT Personal Software          Page 2





                                    SCHEDULE



     additional resources  to  obtain the  required number  if  a  task  is
     critical).  It does give you the schedule based on the resource levels
     specified.  Resource leveling  to the  specified limits is its  normal
     mode and is the primary  advantage of this program over other programs
     of this type.



     Arrow and precedence methods


     Some   texts  use  arrow   diagrams  to   describe  tasks  and   their
     interconnections. The  problem with using a  single line  to represent
     both is that it introduces DUMMY tasks to interlock multiple nodes and
     requires that we describe the entire grid manually.

     The Precedence method  was  introduced later  and is a simpler concept
     which  allows  independent  definition  of each  task  by  listing the
     predecessor tasks required before the task can begin.  The program can
     then construct the equivalent of the  arrow diagram internally (called
     AON or Activity On Node diagrams).  MILE-STONES or EVENTS become tasks
     with zero time and no resources with this method.

     SCHEDULE  incorporates the Precedence Method of task description. This
     provides the ability  to define  the tasks in the form of a model that
     can be used repeatedly. Task descriptions are used to construct a grid
     for each job  based on  the  Job  specifications. These  JOB grids are
     combined  into a  common  Project grid which  represents all the  jobs
     which share  a  single resource pool. In most  project definitions  we
     find  many  processes  repeated  even  though  the  output  product is
     different.  SCHEDULE  allows   a   single  definition   to   be   used
     independently in each JOB.



     Definitions for Project, Job, Task, and Activities


     Texts may  use  these words  interchangeably.  Since they are normally
     discussing a single level of arrow diagrams this is understandable.

     SCHEDULE however  has specific  definitions  which  will be  described
     here. It will be up to you to determine the similarities with the text
     descriptions.

     A Project:  is the entire group of  jobs which are considered within a
     single  grid.  A project has  a single resource  pool.  When  schedule
     processing   is   done  it  is  for   the   project.  There   are   no
     interrelationships (unless manually introduced) between projects.

     A Job:  is a set of tasks. It has  a requested starting and completion
     time which establishes its  earliest starting time and priority. A job
     also specifies the name(s)  of  the  task(s)  which will  produce  the
     desired end result(s). A grid  is then created, by the program, of the


     HITT Personal Software          Page 3





                                    SCHEDULE



     tasks required to produce the JOB.

     A Task:  is  a single job step.  It specifies  the  time duration, the
     resources required, and the immediate  predecessor tasks which must be
     completed before it  can begin. The same task descriptions can be used
     with  other jobs and  produces independent activities. Tasks cannot be
     linked between jobs using predecessors (resources can be used for this
     purpose).

     An Activity:  may be a task or a piece of a task which has been split.
     For  example, if a  task  lasts  many days  and the resource  calendar
     specifies only  8 hours per  day availability, the task will be  split
     into a number  of activities. Also one  resource may be  used on first
     shift and an alternate  resource used  on second shift, resulting in a
     task being split into a number of activities.



     Time considerations


     Project management programs  normally  deal  in  some  arbitrary  time
     duration which could be considered to be  hours, days,  weeks, months,
     or years,  as appropriate to the problem. Some  have the concept  of a
     calendar which allows the program to expand the output schedule into a
     schedule  bar chart or listing with work days, holidays, and  weekends
     taken into consideration.

     SCHEDULE specifies duration  in hours and  minutes since  that  is the
     only scale which is not ambiguous. A calendar can be specified for all
     the  resources,  or  separate  calendars can  be  specified  for  each
     resource.  This  level of  flexibility allows scheduling  of resources
     with defined availability hours and individualized vacation, holidays,
     etc.



     Resource types


     Resources  are  normally  defined  as  an  object  which  can be  used
     repeatedly and is required for the duration of the task to which it is
     assigned.  This  would be a  standard  definition  and  some  programs
     support multiple resources of this type.

     SCHEDULE  not only supports multiple resources  but it also supports a
     number of resource types. This allows modeling to be more realistic.

     Capital  resources, machines or  tools are in  the  standard  resource
     class. They  are available 24 hours per day 7 days a week. They can be
     used repeatedly and  there  usage starts  and stops with the scheduled
     activity.

     In some  cases however a resource is  committed even though  it is not


     HITT Personal Software          Page 4





                                    SCHEDULE



     being  used.  For example: A job requires a truck to  drive to another
     city, the truck is unloaded, and then returns. If the unload or return
     tasks  are  delayed  the truck will still not  be  available for other
     tasks since  it is in the wrong city. The ability to secure a resource
     with  one  task  and release it  with  another  is required.  SCHEDULE
     provides this capability with "Bxx" class resources.

     Labor  resources can  be  used  repeatedly and there usage starts  and
     stops with the scheduled activity. They are not available 24 hours per
     day however, so we use a calendar with working hours to describe there
     availability. With SCHEDULE any resource can have a calendar.

     Some resources cannot be  used repeatedly. Once they are used they are
     gone  (like money).  This  type  of resource has an availability start
     date associated with it and the stocking rate may gate some schedules.
     SCHEDULE  provides  an  "Ixx"  class resource  for  this function  and
     availability start dates can be specified for any resource.

     Some resources are created as the result of a process we would like to
     schedule. We could construct  prerequisite jobs to  the  one requiring
     the resource  but  that  would  force  the  creation  of a  large  job
     consisting of  all  the jobs  requiring the resource.  SCHEDULE allows
     resources to be created by one job for use by others.

     Some times there are a number of tasks within a job that could be done
     in  parallel  except that they are all operating on  the same part. To
     specify the tasks  as prerequisites  would  be preventing  the program
     from shifting the sequence based  on resource availabilities. The same
     kind  of  condition  can exist with  sequences  of tasks. Any one of a
     number of sequences can be started but once that choice is made, other
     sequences cannot be started. SCHEDULE provides JOB resources which are
     used within  jobs  to  force  sequential scheduling  while  allowing a
     variety of sequences depending on resource availability.

     Resources  of the  same  type  may  not  be  interchangeable  in  both
     directions. We might use a car or a pickup truck to go across town but
     we  cannot use a car  to carry a load  of  plywood.  SCHEDULE provides
     generic names and size codes to account for LEVELS of resources.



     Decision making


     In development projects there  are points  in the project plans  where
     decisions must be made.  SCHEDULE allows alternative task models to be
     described  and the  most probable  (or other criteria) selected in the
     job description. As decisions are make the job description is modified
     to reflect  the  choice  and  rescheduling done. The use  of Job class
     resource funneling allows for optional prerequisite specifications.






     HITT Personal Software          Page 5





                                    SCHEDULE



     Summary


     SCHEDULE provides a rich assortment  of resource types to allow a more
     realistic  task  modeling  process.  It  does  not  impose  artificial
     constraints  while providing valid schedules. It also provides  a real
     time update  and tracking  capability to  bridge  between the plan and
     reality.

     The book "RESOURCES MANAGEMENT" by R.  L. Martino, Ph.D.  published by
     MANAGEMENT   DEVELOPMENT  INSTITUTE,  INC.  and  copyrighted  1968  is
     recommended reading.

     The tables used by SCHEDULE can be displayed using the Ctl-F1/F2/F3/F4
     keys. This capability was left active but increases processing time by
     orders of magnitude while the display is active. These displays may be
     of interest to those interested in the academics of the subject.







































     HITT Personal Software          Page 6





                                    SCHEDULE



     CHAPTER 3. CONCEPTS OF SCHEDULING



     Scheduling  (from  WEBSTER's)  is  "a  tabular statement  of  times of
     projected operations, recurring events, arriving  and departing times,
     etc.;(a timetable)."

     To create a SCHEDULE there are several things that must be understood.

     o   The TASKs or steps required to accomplish the objective.

     o   The TIME required to do each task.

     o   The SEQUENCE in which each task must be done.

     o   The RESOURCES that are required to do each task.

     We all do scheduling everyday. When the number of tasks gets large and
     there interactions complex,  then Computers  can help to keep track of
     the complexity.

     The  objective  of  this  scheduling program is  to  process the  data
     supplied in a systematic  way to optimize the resource utilization and
     minimize the overall time required.

     Unfortunately there is no  "OPTIMUM"  schedule since  the  value  of a
     short  schedule  verses  the  minimum number  of resources  is one  of
     judgement not easily specified. A schedule  program  can  provide  the
     ability to locate  the areas  of  sensitivity,  it can  calculate  the
     interactions fast enough  to do "what if's", and it can be a means for
     projecting and tracking progress.

     One of  the objectives of  this scheduling system  is to allow  you to
     define  the TASKS, TIMES,  SEQUENCES,  and RESOURCES in  a way that is
     independent  of  the  interactions  that  result from  conflicts  over
     resources and priorities, and to provide the results in a timely way.

     Schedule processing consists of the following steps:


     o   Input from the user (PROCESSING JOBS)
         -   Job requested
         -   Desired completion date/time
         -   Desired start date/time
     o   From the data base (PROCESSING TASKS)
         -   Get the tasks required to accomplish the job
     o   Build a table with the task data (CONNECTING GRID)
     o   Build a table with the resource data (PROCESSING RESOURCES)
     o   Build a table with the calendar data (PROCESSING CALENDARS)
     o   Calculate earliest start time (CALCULATING EST)
     o   Calculate latest start time (CALCULATING LST)
     o   Determine the next task to schedule (SCHEDULING)
     o   Loop until done and output the completed schedule


     HITT Personal Software          Page 7





                                    SCHEDULE



     CHAPTER 4. MINIMUM SYSTEM REQUIREMENTS



     In order to operate this system you must have the following:

     o   An IBM Personal Computer with a minimum of 192K-bytes of storage.
     o   One diskette drive.
     o   The  IBM Personal  Computer  Disk  Operating System  (DOS  2.0  or
         above).
     o   One additional IBM Personal Computer compatible diskette.

     In addition the following is recommended but not required

     o   An IBM Matrix or Graphics Printer, adapter, and cable.
     o   Two displays, one 80 character per line and one 40.
     o   A high performance fixed  disk as  with the IBM Personal  computer
         XT/AT,  or extra  storage to  emulate  a  disk, or both. This will
         provide improved performance and a smoother operation.





































     HITT Personal Software          Page 8





                                    SCHEDULE



     CHAPTER 5. PREPARING YOUR DISKETTE



     SCHEDULE  is a program  that runs under the IBM Personal  Computer DOS
     (Disk Operating System). "SCHEDULE" need  not  be on the  same disk as
     DOS but DOS must be loaded before SCHEDULE can be run.

     The diskette contains a number of programs which support a menu system
     using batch and command files. These files are  setup to run from  the
     A: diskette but can  be changed to support any disk.  You will need an
     editor  program to  make modifications  to  the xxx.BAT,  xxx.SKB, and
     xxx.GKB files  if you  want to use the  menu's from other  than the A:
     diskette.

     1.  In the xxx.BAT  files look for  all occurrences of "A:" and change
         them to the disk of your choice.

     2.  In the  xxx.SKB and xxx.GKB files look of all occurences of  "ODA"
         and change the "A" to the disk of your choice.

     Normal DOS commands are used to backup your master diskette.

     With the master diskette in the A: drive.

     o   Create a backup of the master diskette using:
                                   DISKCOPY A: B:

     o   Move the program  to a disk with  other programs (DOS for example)
         use:
                              COPY A:SCHEDULE.EXE B:/V

     o   or
                              COPY A:SCHEDULE.EXE C:/V






















     HITT Personal Software          Page 9





                                    SCHEDULE



     CHAPTER 6. OPERATION DESCRIPTION



     You may  wish  to  follow the descriptions given in this section  with
     your Personal Computer in actual operation.  While not necessary it is
     sometimes helpful to observe what is being described.

     Place the Version 1.2 (backup copy) in drive A:

     Load "SCHEDULE" by responding to the DOS prompt.

                             A>A:SCHEDULE A:STATION

     When  the  program  loading  is  complete,  execution  starts  in  the
     copyright frame. Press any key to continue.

     There  are a  number  of different  frames  used to  control different
     aspects of the scheduling process and  we will  discuss the details of
     each  separately. These  frames are  under  control of the  FOREGROUND
     processing  control and have priority over the  BACKGROUND processing.
     Background  processing  occurs  when the  foreground  is  waiting  for
     keyboard  input  and  includes  print  jobs  as  well  as  the  actual
     scheduling calculations. This foreground/background technique provides
     the real time interactive capability of this program.

     First lets see how we get from one frame to another using the Fn keys.



     FUNCTION CONTROL KEYS


     Each of the function keys  is assigned to a control frame. The meaning
     of  these keys are not changed  throughout  "SCHEDULE". You can always
     get from any frame to any frame. Press each key as it is discussed and
     observe the FRAME format.

     Esc will  terminate the program and return to DOS. There will normally
     be a checkpoint taken  in a  file named "xxxx.STA" so re-starting  the
     program does not  start from scratch unless  you ERASE xxxx.STA before
     starting the program. If you have hit this key re-start the program by
     responding to the DOS prompt as before.

                               A>SCHEDULE STATION

     F1 key:  Is  for  HELP.  Pressing F1  again  will  provide  additional
     detail. Pressing F1  while operating  within frames will display  help
     about the particular field the cursor is in.

     F2 key:  Displays tasks  which  are to be started or stopped. On  this
     frame placing the cursor next to the task desired and pressing the "X"
     key will indicate to Schedule that  this task  has indeed  started  or
     ended. This allows rescheduling to be done with real  information when


     HITT Personal Software          Page 10





                                    SCHEDULE



     things don't work out as expected.

     F3  key:  Selects  the  JOB REQUEST  frame.  This frame  controls  the
     contents of a data set named "xxxx.JOB". (xxxx=the project name)

     F4 key:  Will page the interactive activity display backwards.

     F5 key:  Selects the TASK DEFINITION frame where  tasks are described.
     This frame controls the contents of a file named "xxxx.TSK".

     F6  key:  Is  used  with  the  auxiliary  monitor  to  display  detail
     information for the interactive environment.

     F7 key:  Is for RESOURCE DEFINITION where each resource  is described.
     This frame controls the contents of a file named "xxxx.RES".

     F8 key:  Will page the interactive activity display forward.

     F9 key:  Is  for the CALENDAR  DEFINITION where calendars and  working
     hours are described. This frame  controls the contents of a file named
     "xxxx.CAL"

     F10   key:  Provides   the    output    selections   and    processing
     controls.:  Note:xxxx  is the project name specified when SCHEDULE was
     invoked.  A<B:SCHEDULE  C:xxxx  is  possible.  The  default  name   is
     "PROJECT".



     DISPLAY FORMATS AND CONTROL


     The top 23  lines of  the 80  column display are  used by the Frame in
     control.

     The  bottom two  lines are under  control of the background processing
     routines and are independent of the selected frame.

     The left side of line 25 (the bottom line) displays the status  of the
     background processing and  will be  blank  when  no processing  is  in
     process.  Status messages  such as "CONNECTING GRID"  will  be seen in
     this  location  of the screen.  These  are  status only  messages  and
     require no action from you.

     The  right side of line 25 displays the current date and time (24 hour
     time) as provided to the  program by DOS.  The  display  is updated as
     task switching occurs  from the  background to the  foreground. If the
     date or time  is incorrect it should be corrected  by  exiting  to DOS
     (Esc) and using the DOS command "DATE" or "TIME".

     Line 24  (one up from the bottom) is used by the background processing
     to  display  problems  encountered  while  attempting to  perform  the
     background  tasks. Messages such as "PRINTER NOT READY"  are displayed
     on  this line.  See "MESSAGE APPENDIX" for details of  the meaning  of


     HITT Personal Software          Page 11





                                    SCHEDULE



     these messages.

     The remainder of the screen is under control of the foreground program
     (the frame selected). The frames which control  and  update files (F3,
     F5,  F7, F9) use common editing and  record selection  conventions  as
     follows:



     EDIT AND RECORD SELECTION CONVENTIONS


     The keyboard  operates in one of  three modes  depending on  the  data
     field  being   entered.   The  modes  are  upper  case  alpha-numeric,
     upper-lower case alpha-numeric, and numeric.

     Upper case alpha:  In these  fields the  program allows all characters
     to be entered but will translate lower  case characters to upper case.
     This mode is used for fields with significance  to the program in that
     they must be compared or matched  with other names. Forcing upper case
     removes the problem of inadvertent mismatches do to case mismatches.

     Upper/lower case  alpha:  In these fields both  upper and lower cases,
     special  characters,  and  numerals  are  allowed.   It  is  used  for
     information only fields such as TASK DESCRIPTION that becomes  part of
     the output listings but are not compared or matched with other names.

     Numeric  only:  In these fields  only numbers 0 through 9,  and, space
     are  allowed. Any other  character or special  character  will sound a
     note on the built in speaker and the entry is ignored. This  mode will
     also force the  cursor to jump  over slashes  (/) and colons (:).  The
     jump function  is used for  date  and  time fields and speeds entry in
     these cases.

     Insert and  delete are  not allowed in numeric fields as  this becomes
     ambiguous with fixed position fields.

     Field  definition:  Brackets  are  used  to  define  the  entry  field
     associated with the current cursor  position. The  brackets  will move
     under control of the cursor controls. Square brackets [ ] are used for
     alphabetic fields and { } brackets are used for numeric fields.

     Record selection:  The first field of most frames (F3,F5,F7,F9) is the
     CONTROL field.  This  field  specifies a specific  record in the  data
     base. When the cursor is moved out of this field the data base will be
     scanned comparing the  characters from the start of the  field  to the
     cursor (before it was moved). An information message will be displayed
     to the right of the entry field indicating whether or not a record was
     found. If a name match was found  the remaining  data  fields will  be
     filled in. If a  match was  not  found the  data fields  will  be left
     unchanged.

     Leaving the frame (or re-selecting the same frame), using the Fn  keys
     while  the cursor is in  any location other than the first field, will


     HITT Personal Software          Page 12





                                    SCHEDULE



     update  the data base to  the changes  made. Changes can  be prevented
     from altering the data base by first pressing "PgUp" before pressing a
     Fn key.



     CURSOR CONTROLS


     Full screen  editing is allowed within the defined  fields. The cursor
     controls are used to select  the field to be entered or modified.  The
     following describes the rules followed  by the program in  controlling
     the cursor position.

     Right:  Steps the  cursor right  one position. If the end of field  is
     reached the cursor will  go  down and  to the  left  side of  the next
     field.

     Left:  Steps the cursor left  one  position. If  the  beginning of the
     field is reached the cursor will  go up and to  the right side  of the
     previous field.

     Up:  Sets the cursor  in the same position of the next field up unless
     the  new field is not long enough in which case it will be set to  the
     right margin of the new field.

     Down:  Sets the  cursor in  the same position  of the  next field down
     unless the new field is not long enough  in which case it will be  set
     to the right margin of the new field.

     Home:  Sets the cursor to the left  margin of the current field, or if
     already there, to the left margin of the  first field on the frame (as
     with PgUp).

     End:  Sets the cursor to the right margin of the current field.

     PgUp:  Sets the cursor to the first entry field in the frame.

     PgDn:  Sets the cursor to the last entry field in the frame.

     Backspace:  (long  left arrow)  Steps the cursor left one position and
     places a  blank in the  new position.  Trying  to backspace  past  the
     beginning of the field will leave the cursor in the beginning position
     and will sound a note.

     Tab right:  (key above Ctrl) Moves the cursor to the first position of
     the next field to the right, or if none, down.

     Tab left:  (upper case shift and the key above Ctrl): Moves the cursor
     to the  first position of the current field, or if  already  there, to
     the first position of the previous field.

     Enter:  (down  left arrow): Sets the cursor at the left  margin of the
     next field  down. It  is not required for commands as it provides only


     HITT Personal Software          Page 13





                                    SCHEDULE



     the carriage return line feed cursor positioning function.























































     HITT Personal Software          Page 14





                                    SCHEDULE



     CHAPTER 7. CREATING THE DATA BASE



     In order to  do effective  scheduling  we must  be able to  define the
     steps required to do a job  using our knowledge and  experience.  This
     task description process is best approached by  thinking about the end
     result desired and working the problem backwards.



     JOB DESCRIPTION


     First go to  the  JOB entry frame by  pressing the  "F3"  key. This is
     where we  will describe  the final  result desired and  the  dates and
     times  of  our  request.  There  are  three  fields  which  effect the
     processing.

     The  NAME field  identifies the  requestor who is  requesting  an  end
     result JOB  to be STARTED and  COMPLETED at specified times. The other
     fields are used for output listings but do not effect processing.

     Fill in the fields (use your name in the name field)  and  specify the
     name of the task  which results  in the desired end  result as the JOB
     REQUESTED. (for example enter "INSPECTION")

     When  the cursor  was moved  from the  NAME field  the data  base  was
     searched  for a  match of  as many characters as  the  cursor position
     would indicate were entered.  A  message  "NAME NOT FOUND" should have
     been displayed if this was the  first time  this name was entered.  If
     this was not the first time  then the remaining fields will  be filled
     in according  to the data  base, and a  message  "NAME FOUND" will  be
     displayed.

     Background schedule processing will be started when exiting from  this
     frame (if in auto start). Pressing  "F10" in this example will request
     the processing  (exiting from  the job request frame) and will take us
     to  the process control  frame. If  an arrow  is pointing to  the  "A"
     control, processing will  have  started, if not press "S" to start the
     processing.















     HITT Personal Software          Page 15





                                    SCHEDULE



     TASK DESCRIPTION


     Press F5. This is the task definition frame.

     Enter the task name for the job we requested.
                                  (INSPECTION)

     Tasks which  require  more  resources  or prerequisites  than  can  be
     described  on  a single frame  are accommodated by  specifying as many
     records  as  required (max  9, 3 for  our  example).  If you  wish  to
     completely delete a task enter 0.

     Note the resources required to accomplish this task. (MECHANIC)

     A blank quantity field implies "1".

     Note the prerequisites that must be accomplished before this task  can
     begin. (BRAKE CHECK)

     Since we have a record number greater than 1  we can get to the second
     record  by pressing  F5. At  this  record  we can see  the  additional
     resources or prerequisites. (TIRE CHECK)

     Keep pressing  F5 for  as  many records  as  requested  and  make  the
     appropriate entries. (LIGHT CHECK)

     You can  look  at and/or  modify any  task description using  the full
     screen  edit  controls.  You can  find  the other task descriptions by
     entering the name (BRAKE CHECK) and moving the cursor down.

     In  our example  the  tasks  are described in  the sample data base so
     scheduling should complete.  If you get  any line 24 messages see  the
     message appendix for an explanation.

     You may find  the  example task descriptions interesting in that there
     is a variety of  acceptable  forms that may be used. Some  fields  can
     have multiple  entries which are  parsed  (separated with a comma) and
     numeric right  alignment is normally performed by the program. You can
     look at  and  or  modify these  data  base records  by  selecting  the
     appropriate  frame  and  entering the  name (F5, TIRE CHECK,  move the
     cursor down).














     HITT Personal Software          Page 16





                                    SCHEDULE



     RESOURCE DESCRIPTION


     F7 Selects the resource  description frame.  There  are  many ways and
     levels to specify resources so a general discussion about resources is
     probably appropriate before describing each field.

     One kind of resource is a piece of equipment which is required to do a
     task. The equipment can be  used over and  over  again but can only be
     used  for one  task  at a time. This is a  CAPITAL resource and we can
     give it a particular name like "PICKUP TRUCK".

     Another  kind of resource is a consumable which can  be used only once
     and is  then gone. This is an  INVENTORY resource and we can give it a
     particular name like "OIL BATCH 15".

     The third kind of resource is things which  are only available for use
     at  particular times. People normally are in this category and require
     a  calendar  of  available  times.  We  can  give  these  resources  a
     particular name like "JOHN DOE"  or a  name which represents otherwise
     interchangeable resources like "ENGINE MECHANIC". The later case could
     have a quantity other than 1 since there could be any number of engine
     mechanics to choose from.

     The last kind  of  resource  is  an  item to be  operated  on  that is
     particular to  a job. A JOB resource  allows us to define items  which
     might  be  provided  by  the customer such  as  a  car  which needs an
     inspection.

     Within   a   given   category  there   may   also  exist   an   upward
     interchangeability that should be considered. For example a task which
     required  a "PICKUP  TRUCK" could  also use a "ONE TON  TRUCK"  if the
     pickup was not available.  However  a  task which  required a "ONE TON
     TRUCK" could not use the "PICKUP TRUCK".

     The  program  provides   two   facilities   to   account   for   these
     possibilities. One is the GENERIC NAME  which can be added in addition
     to the specific  name. The other facility is the  resource size  which
     can be a number from 0 to 99.

     In  our  example  both the  pickup  and one  ton truck  would have the
     generic name "TRUCK" and an appropriate difference in the size  field.
     Each task description also  contains a size field  which indicates the
     minimum size resource that can be used.

     The scheduling process will  option the resources  for use in order by
     the size field starting at the minimum size specified in the task. The
     size being optioned for use will be  increased a maximum of 30, unless
     the  task  is critical (earliest  start  time = latest start  time) in
     which case it may be increased  to 99. The exception is if  there does
     not exist enough resource either already scheduled  or not, unless the
     number is increased.

     This   generic   resource   size   capability  provides   a   powerful


     HITT Personal Software          Page 17





                                    SCHEDULE



     schedule/cost optimizing capability.  It  is assumed that  the smaller
     resource size number represents a lower cost  and the +30 limit limits
     the  amount  of cost  allowed  unless  the  task  is  critical.  It is
     necessary  to keep the forgoing in  mind when  choosing resource sizes
     and generic names.

     A task can specify either the specific name or the generic name  for a
     required resource as appropriate.



     CALENDAR DEFINITION


     Resources which  use a calendar have  a one character  code which must
     match the code specified on the  F9 frame. Using a blank allows you to
     specify a month  and  year and see  a  calendar for  that date without
     effecting the data base. A blank in the calendar field of the resource
     definition  indicates that the resource is available 24 hours per day,
     7 days per week.

     Many resources may use the same calendar. A separate calendar would be
     required for multiple shifts  or other special conditions such as part
     time employees working individualized shifts. The STATION project uses
     two calendar codes "A" and "B".

     Moving the cursor  below the year will invoke  a data  base search for
     the code, month, and year  specified. A message will indicate  whether
     or  not a match  was  found. If  a match is found the remainder of the
     screen  will be filled in from the data base. If a match is not  found
     the old data is retained.

     A calendar  is calculated  and  displayed on the  right  side  of  the
     display.

     Two time  span's  can be defined for the  days of the  month. If  both
     spans are used in any day (#3) then the span's cannot overlap and span
     2 must be later than span 1.

     Each day of the month can specify a number from 0 to 3 (blank=0).

         0 is for days when the resource is not available.
         1 is for days when the resource is available during time span #1.
         2 is for days when the resource is available during time span #2.
         3 is  for days when  the  resource  is available during  both time
         spans.

     The normal usage of this facility would be  to specify normal  working
     hours (1=starting  time to  lunch,  2=lunch to  end of work day).  The
     calendar  would then contain 3's  for normal working days  and 0's  or
     blanks for days not worked.

     Leaving this display (or re-entering it) by pressing any  function key
     while the cursor  is  below the year entry  area will update  the data


     HITT Personal Software          Page 18





                                    SCHEDULE



     base to reflect the data that was displayed.























































     HITT Personal Software          Page 19





                                    SCHEDULE



     CHAPTER 8. STARTING AND ENDING TASKS



     The  process of scheduling  produces a table in storage  that contains
     projected start  and completion times. This  table  is  maintained  by
     copying it onto  the disk when  exiting from SCHEDULE and is  restored
     when  SCHEDULE  is started.  The  name  of  this  checkpoint  data  is
     "xxxx.STA"  and  allows you to  use  the  personal computer  for other
     purposes without loosing the current scheduling status.

     When the F2 frame is activated  the table is searched to determine  if
     there are any tasks with a  start  time  equal to or  later  than  the
     current time  and that  have  the prerequisites  completed. These  are
     tasks which  should be started, according to the schedule. Placing the
     cursor  next to the selected task and pressing the X key will indicate
     to the program that this task has indeed  been  started  and the table
     will be updated to indicate the current time (actual start time).

     Tasks  which  have  not  been started  at  the  scheduled time  may be
     rescheduled  by  going  to the  F10 frame and re-running  the schedule
     program  (S).  Since they have not been declared to have been  started
     they will be rescheduled.

     At the time a  task is  declared  to  have been  started any inventory
     (Ixx) or buffer (Bxx) resources, used by the task, will  be updated in
     the resource (xxxx.RES) data base.

     The  table is also searched for tasks which are in process (previously
     declared to have been started) and who's  scheduled completion time is
     equal to or later than the current time. These tasks will be listed on
     the right side of the screen. Placing the cursor next  to the task and
     pressing the X key will indicate to the program that the task has been
     completed. The table  will be updated to  indicate the current time as
     the completed time  and if the indicated task was the last  task  of a
     job, the job will be removed from the table and the xxxx.JOB data base
     will be updated to erase the JOBS TO BE DONE field.

     These procedures  are designed  to  allow  new jobs to be added at any
     time and for rescheduling  dynamically  as  real  time  events  occur.
     Listings of the schedule will include an * between  the  date and time
     fields if the time indicated is actual rather than scheduled.














     HITT Personal Software          Page 20





                                    SCHEDULE



     CHAPTER 9. INTERACTIVE STATUS DISPLAYS



     In the interactive job shop environment  there  is a requirement to be
     able  to  re-schedule at any time  to  adjust for the unexpected. If a
     piece  of  equipment breaks down  or an employee  becomes  ill, we can
     access the resource in the data base, set a date and time the resource
     is expected back, and re-compute the  schedule. If a customer does not
     provide an item required to start  the job we can access the job file,
     set a new requested start time, and re-compute the schedule. If things
     are getting backed up, re-compute the schedule.

     With this type of  interaction it is  desirable to be able to  inquire
     into the system rather than getting the detailed printouts each time a
     change is made. For this purpose  the F4, F6, F8 functions can be used
     with an optional color or black and white monitor (40 x 25).

     Pressing  the  F6 key  causes detail  displays  to be  placed  on  the
     optional monitor. Using the optional display has the advantage that it
     can  be  broadcast to  multiple displays and the  display  will remain
     until changed (you can even exit to DOS and run other programs between
     scheduled events).

     There are three  displays that  are supported  on the  monitor for the
     interactive job shop environment.

     1.  Job status display
     2.  Start task detail
     3.  Activity detail

     Job  status display:  In order to answer the  question  "how is my job
     coming" select F3, enter  the name, move the cursor down to select the
     job in question, press F6 to display the status summary.

     Start task  detail:  Frame F2 displays the tasks to be started. To get
     the details about one of these,  select it with  the cursor and  press
     F6.

     Activity detail:  When in other than the first two states the activity
     file  detail  can  be  displayed  by  pressing  F6. This  has  special
     considerations but will normally display the next task to be started.

     The  advantage and disadvantage  of  this display is that  it does not
     require  the internal tables as do the other two interactive displays.
     Detail status can be displayed when the  tables are  being re-computed
     but the logic  of what has  to  be completed before something else can
     start will not be present. Also  milestones (tasks  without resources)
     do not exist on the activity file as they are not activities.

     F6 will locate the first activity which is scheduled after the current
     time. This is normally the next task if you are on schedule.

     F8  will  advance to  the next task in the activity  file. If the horn


     HITT Personal Software          Page 21





                                    SCHEDULE



     sounds the end of file has been reached.

     F4  will move  back  one activity  in the  activity file. If the  horn
     sounds the first record is being displayed.

     The  activity  file  records  are  in  the  scheduled  sequence   (not
     necessarily in time sequence).

















































     HITT Personal Software          Page 22





                                    SCHEDULE



     CHAPTER 10. CONTROL FRAME



     Key letters and numbers are used to activate a variety of functions on
     the F10 frame as follows:



     PRINTER OUTPUT SELECTIONS


     It should be  noted that  the actual printing is done  as a background
     task and  overlaps the disk operations with  the printers line buffer.
     Most SPOOL packages provide no  advantage in print time, require extra
     memory, and delay attempts to terminate unwanted printouts.

     Print  selection  1:  Requests a  listing for the entire Project. This
     lists all  scheduled  jobs and tasks in  order  by  the  start  times.
     Included in the listing is Job name, Task name, Start and Stop times.

     Print  selection 2:  Requests  a  Schedule by Job listing. This  lists
     separately the tasks  for each job. Included in the listing is the job
     name field,  job  description  field,  jobs to be done field, and  the
     requested  start  and  stop times  as the header. The  task name, task
     description, and scheduled start and stop times are tabulated in order
     by the start time.

     Print  selection 3:  Requests  a Schedule by Job listing as  in #2 but
     includes the resources  assigned to each task.  This  listing contains
     the maximum amount of detail about the jobs.

     Print selection 4:  Requests a Schedule for the  Jobs just  started or
     changed. The  format is the same  as #2. This  request does  not reset
     itself  after  the printout  as it is  intended  for  the  interactive
     environment and will  start a printout each time a new job is  entered
     and will print only the new jobs schedule.

     Print  selection  5:  Requests an  ACTUAL  time  listing  for the  job
     completed.  The format is the same as #2. When the last  task of a job
     is  marked as  being  complete (on the F4 frame)  this  printout  will
     capture the  actual data before the table is deleted from memory. This
     request does  not reset  itself as it  is meant to capture the  actual
     task performance in the job shop interactive environment.

     Print selection 6:  Requests a listing of activities for each resource
     selected. The class field in the resource record has 3 characters, and
     the  frame suggests you use "INV, CAP, LAB, or JOB". However there are
     other selections that can be used to make this printout selection more
     meaningful. The only  requirement the  program places on this field is
     that any class that has a first letter of "I", "B", or "J" get special
     attention,  the remainder of the field can be used to select groups of
     resources to print with a single request.



     HITT Personal Software          Page 23





                                    SCHEDULE



     If  you  would  like to  provide  an  activity  listing  for a  single
     resource, give  it a  unique class code within  the first letter class
     desired.

     Print selections 7, 8, 9, and 0:  Requests  a listing of the data base
     files.  When  developing  complex  project  task  definitions   it  is
     sometimes useful to have a hard copy reference. Also when decoding the
     internal  tables  the  numeric  codes  refer  to  the  record  numbers
     displayed in these listings.

     Selection H:  Allows you to enter  a line of data to be printed as the
     first line of each  page of printer output. This is  normally used  to
     print the security classification.

     Selection R:  Resets all print requests. Any printout in  process will
     continue.

     Selection T:  Terminates  the printout in process.  The next  printout
     selected will start  after the termination unless they are reset using
     "R" or multiple terminate "T"s are entered.



     BACKGROUND PROCESSING CONTROL


     Selection  S:  Starts   the   scheduling  program   to   schedule   or
     re-schedule. This  can be  done at any time but may obsolete  previous
     resource  allocations   and  job   estimates   (in  process   resource
     allocations are  preserved). Tasks marked as started or completed will
     be accounted for as the  process is  not starting over by rescheduling
     (unless you first erase the "xxxx.STA" file).

     Selection A:  Provides an automatic "S" function each time the F3 (JOB
     REQUEST) frame updates the data base with a new or changed job request
     or when a task is completed (X in frame F2 IN PROCESS).

     Selection E:  Tasks to be started or ended can be displayed before the
     actual time has arrived. The amount it will be early is determined  by
     the value entered here.
















     HITT Personal Software          Page 24





                                    SCHEDULE



     Selection C:  The color attributes can be set using this function.

         CODE      COLOR      MONOCHROME      Use F1 HELP to find the position

        @ or 0 = Non Display  Non Display       1 = 40x25 Date/time
        A or 1 = Blue         Underscored       2 = 80x25   "
        B or 2 = Green        Green             3 = 40x25 Fixed format
        C or 3 = Cyan            "              4 = 80x25   "
        D or 4 = Red             "              5 = 40x25 Data base data
        E or 5 = Magenta         "              6 = 80x25   "
        F or 6 = Brown           "              7 = 40x25 Disk command display
        G or 7 = White           "              8 = 80x25   "
        H or 8 = Gray         Non Display       9 = 80x25 Background processing
        I or 9 = Light Blue   Bright Green     10 = 80x25 Help displays
        J or : = Light Green     "             11 = 80x25 Keyboard data
        K or ; = Light Cyan      "
        L or < = Light Red       "
        M or = = Light Magenta   "
        N or > = Yellow          "
        O or ? = Bright White    "



     DATA BASE MAINTENANCE


     Data  base  maintenance  provides  for   the   automatic  deletion  of
     individual records  in  the  data base. The  file  size will  not  get
     smaller but space will be created so that records can be added without
     increasing the file size.

     Selection D:  When the arrow  is pointing  to the "D", records will be
     deleted as follows.

     Job Request records  will be deleted at the completion of the job. The
     REQUESTED JOBS field is made blank when the last task is completed and
     the record will be deleted the next time scheduling is done.

     Task  records are not  automatically deleted. Entering  a zero for the
     number of records required will delete task definitions.

     Resource  Definition records  are deleted when the quantity is "0000".
     If you would like to delete a record put "0000" in the quantity field.
     Inventory records will have this value when used up.

     Calendar records will be deleted when the year  and month is less than
     the current time. Be sure the DOS  date is correct  or  you  may loose
     some calendars.

     Selection U:  Task and resource data base files can be protected  from
     accidental  alteration by locking these files. Each depression of  "U"
     reverses the state of the lock.




     HITT Personal Software          Page 25





                                    SCHEDULE



     Selection  M:  Max Activities  set  the  maximum  number  of  activity
     records that will  be written by the scheduling process. Each activity
     record is  24 characters in length so  a space of 24 times the  number
     entered in maximum activities could be required for the activity file.
     In addition  a xxxx.TMP file  is  created and is  renamed xxxx.ACT  so
     additional space is actually required.

     You  will normally want all the scheduled activities recorded. However
     there  are  cases where a huge number of activities  are generated and
     are of little value. For example: in project planning over a number of
     years it is not necessary to see each employee go to lunch and go home
     (2 activities) each day when the task lasts  for  months. Limiting the
     size of  the  activity file has the effect  of being able  to  see the
     detail activity for the next n days without generating huge  listings.
     You can play with the number to get the desired detail look ahead.

     The effect of loosing activity records is that a resource  will not be
     listed with the task  and inventory records will not be updated if the
     task is started. You should allow enough activity records to cover the
     period between re-scheduling.

     Running   out   of  disk  space  while  scheduling  is  normally   not
     catastrophic  as long as there is room to take a checkpoint. Recording
     of  activities  will  stop  but  scheduling  will  continue.  The  MAX
     ACTIVITIES number  will  be  automatically  adjusted downward  to  the
     actual available space.






























     HITT Personal Software          Page 26





                                    SCHEDULE



     CHAPTER 11. SPECIAL RESOURCES



     There are three types of resources that the program handles in special
     ways.  These  resources provide  some  of  the  powerful task modeling
     abilities of the program.



     INVENTORY RESOURCES


     Resources which use a  type code which starts  with the letter "I" are
     considered to be  inventory type resources. These  are subtracted from
     the data base when used.

     The generic name of the resource can be used to allow selection from a
     number of inventory specifications which may be available at different
     times.  The size code  can  be  used  to control the  sequence  of the
     selection.

     This  facility can also be  used  to control the rate  at which things
     (like money)  are  used.  Making the  resources  available  using  the
     resource availability date  and specifying the amount required in  the
     task description will constrain the starting time of tasks.



     BUFFER RESOURCES


     The  name  comes from  the idea  of  modeling  a production line where
     buffers  separate  operations  which  are defined  as  tasks.  A given
     station  can stop for a period  of  time  without stopping  the  other
     stations to the limit of the buffer.

     One example  of  the use of this buffer type resource is  available in
     the TUTOR use of  a resource named  "BLD".  The generic  name of  this
     resource is "XBLD" and the  data base shows a  quantity of 3. When the
     task "CAR TO GARAGE" is started it requires one BLD resource. When the
     task "CAR TO LOT" is started it requires one XBLD resource.

     What is happening is that when  the NAME of a buffer resource is  used
     the resource  is subtracted  from the available  quantity in  a manner
     similar to inventory resources. That  is the resource is  not returned
     for use when  the task is completed. When the GENERIC NAME is used the
     quantity is  added to the available quantity.  In  this way the number
     of cars in the building  is limited to three  by the original quantity
     of this resource.

     The same function  can be used to create  a  resource with one job for
     use by  others.  If a  number  of  jobs  cannot  be  started  until  a
     specification is available and this specification is the end result of


     HITT Personal Software          Page 27





                                    SCHEDULE



     scheduling a job. This could be  modeled by defining a "SPECIFICATION"
     resource with a generic name of "RELEASE SPEC" and a quantity of zero.
     The  tasks which  require  the  specification  before  they can start,
     specify  a resource requirement of "SPECIFICATION" with  a quantity of
     one. The task which releases the specification and is gating the other
     jobs  would  specify a resource  requirement  of "RELEASE SPEC"  and a
     large quantity (9999).

     The generic names of Bxx class resources should be unique.



     JOB RESOURCES


     Job  resources  allow  a  single  resource  specification to  be  used
     independently within a job.  The  program  will create  an  additional
     resource for each job that uses it. This concept provides for the idea
     that a number of tasks could be preformed on this  job resource except
     that there are restrictions on how many can be preformed at once.

     Generic name job  resources:  The  task specifies the generic  name of
     the resource  which is a type Jxx. This will limit the number of tasks
     which can be executed in parallel  to  the  quantity provided  without
     restricting the sequence in which they are done.

     An example of this  is in the  TUTOR resource  "CUSTOMER  CAR"  with a
     quantity of 1.  The generic name "CAR" is specified in the tasks which
     require the car as the object to  be operated on.  Only one  operation
     within the job which specifies this resource can be executed at a time
     because  the quantity of this resource is 1. Specifying a  quantity of
     two  would  allow  any  two  tasks  (within  the  constraints  of  the
     prerequisite task requirements) to be executed simultaneously.

     The resource  name should be selected to describe the  resource in the
     printouts and display.

     Specific name job resources:  When the specific name of a job resource
     is  used  it is  handled  in  a  vary  special  way which  allows  for
     controlling task sequences in addition to allowing for  the concept of
     job parameters and decision points within a job/task model.

     The  TUTOR data base uses this  feature to  control  the start of task
     sequences  which  cannot  be  interrupted  as  well  as  allowing  the
     individual task  requests (LUB, OIL,  FILTER,  ETC.)  to  be specified
     within the  job description  and inserted  at  the  appropriate points
     within the  job grid.  This  facility essentially  provides a resource
     method of describing task sequences.

     The rules followed by the program for specific named job resources are
     as follows:


     o   Of the tasks which have their prerequisites satisfied.


     HITT Personal Software          Page 28





                                    SCHEDULE



     o   Select  the  tasks  which  do  not specify  a  specific  name  job
         resource.
     o   If none select the  tasks with the lowest size requirement for the
         specific name job resource.
     o   Of the  tasks  selected  apply the other  resource constraints  to
         select the task to schedule.

     It may be helpful to study the TUTOR.TSK file to gain an understanding
     of how this facility is used.















































     HITT Personal Software          Page 29





                                    SCHEDULE



     CHAPTER 12. ASSIGNMENT TRACKING



     If you happen  to be managing a  group of people who's assignments are
     to respond  to individual questions (staff work)  then SCHEDULE can be
     used to track  these assignments without really  doing any scheduling.
     Some people call these assignments "ToDo's".

     In this environment the program is used to track the ToDo's

     o   Name of the assignment and the description

     o   Name of the employee assigned the task

     o   Amount of time before a review should be done

     o   Date and time the assignment was entered into the system

     o   Date and time the employee was told of the assignment

     o   Reminder when the task should be completed

     o   Date and time the assignment was completed

     o   Printouts of all active assignments

     o   Printouts of all active assignments by employee

     o   Printouts of completed tasks for the department activity file

     As  the questions arise the new jobs are entered into  the system. The
     name and description field of  frame 3  (F3)  are  filled in. SCHEDULE
     will  automatically set the  starting and ending time  to  the current
     time thus providing the first  time stamp. If the  name  of the person
     that is  to receive the  assignment is known,  it should be entered in
     the  JOBS TO  BE DONE field.  If the name is  unknown  a name  such as
     "ASSIGN" should be entered.

     Processing the schedule will cause this job to be  displayed on the F2
     frame  under "TASKS TO BE STARTED". This  is  the  list of assignments
     which must be communicated to  the employees. Pressing  an "X" next to
     the task will indicate to  the program that the task has been assigned
     and the time will be recorded.

     Pressing  F2  again  will  display  all  the  ToDo's  that  are  to be
     completed. When  they are completed, position  the cursor  next to the
     task and press  "X". This will indicate to the program  that the  task
     has been completed and the actual time will be recorded.

     When the task completion time is due it will appear on the  right side
     of the F2 frame under "TASKS TO BE COMPLETED".

     The  F10  5 function will provide an automatic printout  of  completed


     HITT Personal Software          Page 30





                                    SCHEDULE



     tasks  which  can  be  placed  in the  department  activity  file  for
     posterity. The  requested start time is the time you first entered the
     ToDo.  The  task  start  time  is  equal  to the  time  the  task  was
     communicated to the employee. The  task completion  time was the  time
     the answer was communicated to you.



     JOB DEFINITION


     Each task is defined as a job. The person  to  be  assigned the job is
     entered into the "JOBS TO  BE DONE" field. If a time duration  is also
     to be set the duration becomes part of the name. For  example "JOHN  1
     WEEK" for employee JOHN and a duration of 1 WEEK.



     TASK DEFINITION


     Each employee's  name (nickname etc.) can  be used as a task name. One
     task should also be created with the name "ASSIGN".

     The tasks which are given  a name that implies an  unlimited  duration
     should  be given  a large duration  (9999). The tasks which  specify a
     time  in  addition to  the  name  are  given appropriate  durations (1
     week=7x24=168 hours). The hours/day field should be left blank.

     In the resource field, enter the name of the person referred to in the
     task name. The quantity and size fields should be left blank.

     No prerequisites should be specified.



     RESOURCE DEFINITION


     Each  employee  is defined as a  resource by  using their name  as the
     resource name. An entry is also made for a resource named "ASSIGN".

     A type  of Lxx is  used where  xx is unique (such  as initials).  This
     allows  us  to use the L**  option with the  F10 print  6  function to
     provide listings  of all the employees, or we can use  the Lxx  to get
     individual listings.

     The quantity field is set to a large number (9999).

     The size and calendar fields are left blank.






     HITT Personal Software          Page 31





                                    SCHEDULE



     JOB FILE LISTINGS


     Printing  the entire  job file will  provide  a  listing  with all the
     description  information of the outstanding jobs. If  you wish to sort
     this file it should  first be  copied  to a new project  name, sorted,
     then printed from that new  name.  A batch file and .SKB  command file
     can be  setup to provide  a single operation  that will copy the file,
     sort it using DOS sort,  start SCHEDULE using  the new  project  name,
     enter the keys to cause the printout, and exit SCHEDULE.



     FRAME 10 CONTROLS


     For this application the F10 controls should be set as follows:

     o   5 on to provide automatic summary task listings.

     o   A on to provide automatic recalculation when new jobs are entered.

     o   D on to provide  automatic  job  record  deletion  when tasks  are
         completed.

     o   M set to 9999 to save all started activities.



     SUMMARY


     There are other  ways of  structuring the task data base  which may be
     more appropriate for your  application.  For example the  persons name
     could specify  a start and end task and optional duration tasks  could
     be inserted by the  program using  the Jxx resource funneling function
     with appropriate size  codes. This approach would not require  as many
     task descriptions if a large number of  different time  durations were
     required for a large number of employees.

     The example here is simpler and  is offered as a suggestion to get you
     started.














     HITT Personal Software          Page 32





                                    SCHEDULE



     CHAPTER 13. MEETING CALENDARS



     Keeping track of your meeting calendar  is  a useful  application that
     can  be  combined  with  project   management  and   staff  assignment
     applications  into  a  single department project file. It  can also be
     done independently to produce a daily listing of your meeting calendar
     to be carried by you.

     This application will provide the following:

     o   Time stamp of the date/time the item was entered
     o   Scheduled date/time of the meeting
     o   Time stamp of the date/time the meeting was started
     o   Time stamp of the date/time the meeting ended
     o   Optional listing of each meeting for your activity file
     o   Optional listing of all pending meetings in order by date/time
     o   Optional listing of all pending meeting conflicts



     JOB DESCRIPTION


     The name of the meeting will be entered as a job on the F3 frame.

     The duration of the meeting will be the "JOB TO BE DONE". For example:
     ".5 HRS" for a one half hour meetings.

     The requested start time must be set to the date/time of the meeting.

     The requested completion  time was  set by the program to the  current
     time and  should be left unchanged as it represents the the time stamp
     for the time the meeting was entered into the system.



     TASK DESCRIPTION


     A task description is created for each possible meeting time duration.
     For example:  ".5 HRS", "1 HR", "1.5 HRS" ... "8 HRS" would be used as
     the task names.

     The task duration is set to the duration indicated by the task name.

     The hours/day field is left blank.

     The resource field will  specify your name (nickname) and the resource
     "REP". For example: "JOHN,REP".

     The quantity, size, and prerequisite fields are left blank.



     HITT Personal Software          Page 33





                                    SCHEDULE



     RESOURCE DESCRIPTION


     One resource is created with your name  as the resource  name and with
     your nickname as  the generic name. Make the  class equal to "Lxx" and
     the quantity field equal to "9999".

     The next resource is created with "CONFLICT" as the resource  name and
     with "REP" as the generic name. Make the class equal to "Lxx" where xx
     is  the same as was  used  with your  name so the CONFLICTs will print
     anytime  your resource class  is requested for  print.  Make the  size
     field equal to "1" and the quantity field equal to "9999".

     The  last resource  is created  with "DUMMY" as the  resource name and
     with "REP" as the generic name. Leave the  class and size fields blank
     and make the quantity field equal to "1". The  quantity represents the
     number of meeting you can attend simultaneously.



     MEETING CALENDAR LISTINGS


     The  F10 print 6 of  "Lxx"  will print a listing of all the  scheduled
     meetings in  order by the date  and time.  If  any conflicts  exist an
     additional listing will be created which indicates the conflicts.

     You may wish to send this file to the disk using the "ODx" command and
     setting the lines per page  to zero using the "L00" command. This will
     allow you to browse your schedule using an editor program such  as the
     "IBM Personal Editor".



     INTERACTIVE MEETING REMINDERS


     Using the F10 "E" command  you  can set the amount of advanced  notice
     you would like  to  have regarding the upcoming meetings. For example:
     setting 8 hours would allow you to see all of todays  events on the F2
     frame.



     AUTOMATIC OPERATION


     A  batch  file in combination  with  a command  file can be  setup  to
     automatically display  your events according to your own routine.  You
     may wish  to have your days agenda displayed  when  you first turn  on
     your system, press Esc  and enter a mode where each event is displayed
     five minutes prior  to its scheduled time,  press Esc  again and print
     the entire calendar to disk, exit the program and invoke and editor to
     display your entire schedule on the screen.


     HITT Personal Software          Page 34





                                    SCHEDULE



     See  the chapters  "Keyboard  Command File", "Ideas  for  the expert",
     "Program  exit return codes to DOS" and  your DOS manual under "BATCH"
     for details.





















































     HITT Personal Software          Page 35





                                    SCHEDULE



     CHAPTER 14. DEVELOPMENT PROJECT PLANNING



     SCHEDULE  provides  a  number of  features which allow  the process of
     "Development Project Planning" to be  done in levels,  while providing
     continuity in the projects scheduling and tracking functions.

     The service  station  job shop environment is a  situation  where  the
     tasks have been  done  before  and  are very well understood.  In that
     environment  "tasks" and  "resources" remain  relatively  constant and
     jobs become the variable. Not so with development projects.

     With  development  projects  the  plan  has varying  detail  available
     depending on how far out we  are looking.  Typically we  will  have  a
     general idea  of how to go about attacking the project but do not know
     details. Therefore we would like  to be able to schedule with variable
     levels of detail.

     Most development projects have major phases like:

     o   Research

     o   Plan

     o   Design

     o   Prototype (simulate or model)

     o   Debug

     o   Release (to manufacturing)

     o   Product Support

     These phases represent  the points where the responsibility moves from
     one  organization  to  the   next.  These  are   normally   considered
     MILE-STONES and represent the points at which an output from one group
     is available as an input to the next group.

     It  is  important  for  the project model  to  have  boundaries  which
     represent  the actual organizational  responsibility boundaries of the
     project.  Most  organizations  have hierarchies and  the detail levels
     described here could be considered to be levels in this hierarchy.

     Another way  of looking at the levels  is as a "TOP  DOWN DESIGN", and
     since the final detail is added to the bottom, it becomes a "BOTTOM UP
     PLAN" much like the Eastern Cultural Methods.

     "QUALITY plans" also have characteristics which can be mapped into the
     process.  Defining the  input/output and  required steps  to produce a
     measurable quality process independently  from  schedule  and resource
     constraints is a powerful  tool. As pressure is applied  (schedule  or
     resource)  the steps being bypassed become  apparent. Choices can then


     HITT Personal Software          Page 36





                                    SCHEDULE



     be made intelligently to compromise the quality, schedule, or cost.

     The following detail levels describe ways or  levels that SCHEDULE can
     be applied to  development type projects.  You may  wish to jump in at
     some level  with your  project, or  you may choose to use  the  entire
     process.  SCHEDULE allows  you to  plan,  track, and  project from any
     level. It is unique in its ability to allow a great deal of detail.



     DETAIL LEVEL 1:


     This detail level is  equivalent to the level provided by most project
     management programs.  We specify an unconstrained resource environment
     and  impose the market requirements  (requested  completion).  If  the
     requested completion time cannot be  accomplished the critical path is
     defined so that we can adjust our assumptions accordingly.

     The  objective of  this  level is to bring the  planning  to the point
     where each of  the  independent areas  can independently  asses  there
     ability to  meet the overall  schedule. The output  from this level is
     used to commit  resources from  each of the effected areas to complete
     the definition of detail level 2.

     Our first pass would define each of the  phases, of the project,  as a
     task with a duration and the previous phase as a prerequisite task. As
     the responsible  areas  estimate the  resource requirements  they  are
     added to the task descriptions.



     JOB definition


     There is only one  job. It requests the final task (PRODUCT  SUPPORT),
     and has a requested start  and completion time. These same assumptions
     are used by the planning department, along with a product description,
     to estimate quantities etc.



     TASK definition


     Each phase becomes a task with the previous phase as its prerequisite.
     It is an over simplification to imply that there would be only 7 tasks
     however. The grid should contain as  much detail as  is available from
     historic information  or planning judgement.  There may be hundreds of
     tasks defined at this level. This level of scheduling is equivalent to
     the only level provided by most project  management systems. The  task
     duration  is estimated in hours but we normally  are not  thinking  at
     this detail  level.  The  number  to  use  is derived  by  doing  some
     multiplication.


     HITT Personal Software          Page 37





                                    SCHEDULE



         With 8 hour days and 5 day weeks

             1 day = 8 hours

             1 week = 40 hours

             1 month = 150 hours (173 without holidays/vacations)

             1 quarter = 500 hours (520 without holidays/vacations)

             1 year = 2000 hours (2080 without holidays/vacations)

     SCHEDULE allows you  to define up to 5 years (9999 hours)  as a single
     task duration (assuming 40 hour weeks).

     Since the resources will not  have calendars, at this detail level, we
     will set the HOURS PER DAY to match our assumptions.  With 8 hour days
     and 5 day weeks the hours/week will be 40 so we should use 6 hours/day
     (6x7=42) since the program will assume 7 day weeks.  This field allows
     us  to  specify approximate time scales  without requiring  calendars.
     When we  start specifying  calendars with  resources we will  make the
     hours/day = 24.

           32 to 38 hour weeks use 5 hours/day

           39 to 45 hour weeks use 6 hours/day

           46 to 52 hour weeks use 7 hours/day

           53 to 59 hour weeks use 8 hours/day   hours/week / 7 = hours/day

           60 to 66 hour weeks use 9 hours/day

           67 to 73 hour weeks use 10 hours/day

           74 to 80 hour weeks use 11 hours/day

     Usually,  at  this  level,  projects  are  estimated  as  people-days,
     people-weeks,  or  people-months and  assume  calendar durations.  The
     estimated effort required  to accomplish  a task should  always be the
     product of the resources specified times the duration specified.

     SCHEDULE  always uses hours  as the  duration  so that functions  like
     putting  on a  2nd shift or  scheduling  overtime  will  automatically
     reduce  the calendar time. Increasing the hours/day field, over normal
     working hours, is equivalent to adding overtime.



     RESOURCE definition


     Only  the main resources are specified  and these are  specified  at a
     high  level.  For  example we  might  require  Researchers,  Planners,


     HITT Personal Software          Page 38





                                    SCHEDULE



     Engineers, Technicians, Manufacturing Engineers,  etc. We  will create
     one  resource definition  for  each  of  these  and  specify  a  large
     available quantity to allow an unconstrained (best possible) schedule.



     The critical path


     The  output listing prints  an "*" before the task  name if the  float
     time is zero  or negative. With an unconstrained resource environment,
     as described here, this  will be the tasks which must  be improved  to
     improve the schedule (The Critical Path).



     DETAIL LEVEL 2


     This level  becomes  appropriate  when each  area of the  business  is
     committed  to the  schedule derived  by detail level 1. Here we define
     the output product of each area that is required before the next group
     can  start, and  we will set the requested start and completion  times
     for each area to the committed times negotiated using detail level 1.

     To do this  we will  define additional JOBs, one for each of the steps
     previously defined at  the points where the  responsibility moves to a
     different organization.  We  will also alter the  task descriptions so
     that  rather  than connecting the  tasks  with  prerequisites  we will
     specify a  resource  as being the product  produced  by  one group and
     required by  the next. This allows  us  to  plan  and track  based  on
     organizational boundaries.

     You may find later that it  is desirable to break  the  project into a
     number of projects based on the  same organizational boundaries.  This
     will allow scheduling at a lower  level within organizations that have
     responsibilities to multiple projects.  Here we would create a project
     that is really jobs from multiple  projects  that are sharing the same
     resource  pool.  In this case the schedules  are manually  controlled,
     between projects, using the availability dates of the output resource.

     SCHEDULE  is  unique  in its  ability to use "Bxx" class  resources to
     represent  a  resource  created  as the result of  executing a set  of
     scheduled tasks. This resources  creation represents a "Mile Stone" in
     most project management systems but  is more  realistically a resource
     as described here.



     JOB definition


     Add a  job for  each organization that  will have responsibilities  to
     this project.  The requested  start and  end times  were  derived  and


     HITT Personal Software          Page 39





                                    SCHEDULE



     agreed to  during detail level 1 planning. Under JOB REQUESTS we  will
     specify the task(s) that produce the end result resource.



     TASK definition


     Modify   the  task  descriptions  for   the  tasks  which  called  out
     prerequisite  tasks  from  other  organizations.  We will  remove  the
     prerequisite requirement and  instead specify the resource created  by
     the other organization.

     The  tasks,  specified  as  the  requested  tasks  in  the  added  job
     definitions,  will be  modified to  add  the creation  of the resource
     which is its end result product.



     RESOURCE definition


     The  "Bxx" class resources  are added as appropriate with the quantity
     field left blank. This describes the  resource even though it does not
     exist until the  task which creates  it is  executed. The GENERIC name
     will be used  in tasks descriptions which  are  adding to the pool and
     the  SPECIFIC name  (top line) will be used in task descriptions which
     are using Bxx class resources.

     At this point it may also be appropriate to increase the detail of the
     labor resource. Rather than a single resource "ENGINEER" we could keep
     that name as the generic name and use specific names such as ASSOCIATE
     ENGR, STAFF ENGR, ADVISORY ENGR, SR ENGR, with appropriate level codes
     and quantities. If  we were thinking ahead, we would  already have the
     levels specified in the tasks.

     [Caution: The specific name(s) should not equal generic name(s).]



     The critical path


     The output  listing  prints an "*"  before the  task name if the float
     time  is zero  or  negative. Since this detail level  is  not resource
     constrained this will be the critical path. Each job's  start/end time
     was specified independently in this case so some jobs may  not display
     critical paths while others (in sequence) may.

     At this level  we  should be making adjustments between the amount  of
     resources, and the duration of the tasks, to balance the schedule. For
     example we might decrease the  resource of  the noncritical  tasks and
     increase  the resource of critical  tasks while adjusting the duration
     appropriately until an acceptable schedule is obtained.


     HITT Personal Software          Page 40





                                    SCHEDULE



     DETAIL LEVEL 3


     The objective of this level  is to obtain agreement and commitment for
     the  resources required  to  accomplish  the  tasks  on  the  schedule
     previously determined.

     This is not as easy  as  it might sound. Normal variables are Quality,
     Resource, and  Schedule. Quality gets compromised  by bypassing  steps
     (tasks)  in the defined process (like documenting your work).  Here we
     can only vary resource and schedule, and we will track the steps.



     JOB definition


     Unchanged



     TASK definition


     Unchanged



     RESOURCE definition


     The  resource  definition is modified to reflect the assumed  resource
     levels.

     Some  reductions of  resource will cause little or no  schedule change
     due  to  the  resource  smoothing that  will  be accomplished  by  the
     program. Printing the resource utilization of the resources will  give
     you the data required to determine the peeks and valleys.



     The critical path


     When scheduling is  done while resource constrained it is possible for
     the job to be noncritical when scheduling the first tasks but, because
     of delays acquiring resources, later tasks become critical. To see the
     entire  critical   path  you  can  temporarily  change  the  requested
     completion time to force the "*" display in the early  tasks (SCHEDULE
     used "local float" for this determination).






     HITT Personal Software          Page 41





                                    SCHEDULE



     DETAIL LEVEL 4


     This is the level where calendars are  imposed on  the plan. With this
     level of  detail  it  is possible  to  use the interactive  update and
     re-schedule functions of the program to track and  project changes. If
     delays occur corrective  actions can  be taken (more resource applied,
     more shifts, etc) and the corrections effect projected.

     At this  level the program is allowed  to switch resources at calendar
     hour/minute boundaries  depending on the priority  of the tasks.  When
     rescheduling  with calendars  for  the  first time there  may  be some
     critical  task  improvements  because  of  resource switches  and task
     splits.

     Also the program may  allocate one resource on first  shift and others
     on 2nd shift  to improve the  schedule  as  allowed by  the calendars.
     Without calendars the HOURS/DAY field allowed the idea of overtime but
     not  resource   changes.  With  calendars  overtime   and  shifts  are
     controlled by the calendars.



     TASK descriptions


     Clear the hours/day field (blank = 24).



     RESOURCE descriptions


     Specify the appropriate calendar(s).

     Split resources  (same generic  name) into  as many groups  as require
     separate calendars.



     CALENDAR descriptions


     Describe the appropriate working hours for each calendar.



     QUALITY PROGRAMS


     Quality is defined as  "Meeting the  Requirements"  and is emphasizing
     the  idea  of  doing it right the  first  time  rather  than  building
     expensive  techniques  for fixing it  later. Some  would  consider the
     techniques being discussed as just good management style, while others


     HITT Personal Software          Page 42





                                    SCHEDULE



     believe its a new way of doing business.

     Quality is  currently  getting a lot  of attention from U.S. business.
     Most are modeling their programs after Japanese business. A  number of
     things provide the foundation of most quality programs:

     o   Understand the customer's requirements.

     o   Involve the implementers in developing the plan.

     o   Develop a process which emphasizes early detection and  correction
         of flaws.

     o   Define quality measures so that improvement can be identified.

     o   Identify the cost of quality.

     o   Involve your suppliers in defining your requirements to them.

     One technique currently being used to help manage  quality programs in
     some corporations is known as DAA (Department Activity Analysis).

     DAA defines every operation or task as a PROCESS.

     Each PROCESS has inputs, value added action, and outputs. The input is
     treated  as coming from  suppliers and  the output  is that  going  to
     customers.  The discipline for defining this process is much the  same
     as  that  required  for  the   project  management   steps  previously
     described.

     Applying DAA to  the  project management  approach makes  it a quality
     program rather than just a planning tool.

     Each task of a process should be  described in detail and developed by
     the  group responsible for  implementing the  tasks. Quality standards
     and measures should also be defined by the people responsible.

     SCHEDULE allows the durations and  required resources to  be described
     independently from the schedule  and  available resources. Quality  is
     sometimes compromised by skipping steps in an effort to meet schedules
     with  limited  resources.   SCHEDULE  varies  the  schedule  with  the
     available resources but keeps the process the same.

     SCHEDULE  provides tracking  which  insures that  all  the  steps  are
     executed. Resources  can  be  defined to  represent the product  being
     developed  by  one  group  and  required  for  the next  step  in  its
     completion.

     SCHEDULE will not automatically  insure quality, but it can provide an
     important component in the control of the process and resources  which
     will  effect the quality of the product or  output. SCHEDULE used with
     DAA helps  departments to understand the  product they  are producing,
     the  processes required to  produce  it,  and  the interdependences on
     other organizations.


     HITT Personal Software          Page 43





                                    SCHEDULE



     CHAPTER 15. IDEAS FOR THE EXPERT



     INTRODUCTION TO THE EXPERT SECTION


     SCHEDULE was written for the expert. Prompts don't get  in your way as
     they are  provided only with error detection or  requests for help. It
     is meant to be  fast and efficient if  you know what you would like to
     do.

     SCHEDULE  is  vary  flexible  and  can  be  used  in   any  number  of
     applications. It can  also  be  setup  by the expert for use by people
     with  limited  knowledge.  A  particular  application  can  limit  the
     flexibility to keep people out of trouble.

     This section is devoted to ideas that may improve  your efficiency  in
     using the  program. Ideas  which may  have  general applicability  are
     described here  and may stimulate your own ideas. Its a  list of hints
     that may be of help to the experienced user.

     You will find  that  SCHEDULE's disk  command language in  combination
     with DOS's batch facilities  will  allow  you to tailor your operating
     environment to  your  particular needs.  These command  languages were
     used  to provide the demonstration material which demonstrates some of
     its power and flexibility.



     USING SCHEDULE OUTPUT AS DATA FOR OTHER PROGRAMS OR PRINTERS


     The  normal listing outputs can be  directed to a selected  disk using
     the F10 output unit selection  parameters.  This  creates a  data file
     which  if  directed to the  printer  will  produce  exactly  the  same
     printout as would be  produce  if it  had been  printed directly. This
     file  contains  all  the  printer  control   characters,   page  eject
     characters, headers, and page numbers  with  spacing  appropriate with
     the page size setting.

     Making  the number of lines per page parameter on the  F10 frame equal
     to  "00" eliminates the  headers and printer  control characters. Each
     line  is  ended  with  the  normal  ASCII  carriage  return line  feed
     characters (13,10) with the exception of the last line of each listing
     which contains a carriage return eject (13,12). Other printer controls
     have been stripped and an infinite page length is assumed.

     This form is more  easily used by other programs which would otherwise
     have to deal with the control characters and  is also in a better form
     for other printers which do not use the IBM matrix printer controls.

     You may also wish to  use this form when communicating thru the RS-232
     serial  adapter or  when connected via terminal  (327x) type emulation


     HITT Personal Software          Page 44





                                    SCHEDULE



     adapters to your central system.



     BUILDING LARGE SIMILAR FILES


     With some applications a large number of  tasks and/or  resources must
     be  created  which are  similar  except  for  small changes. There are
     methods which will reduce the amount of data entry required.

     Solution 1:  Takes advantage of the zero length name entry function to
     re-select the last record.


     1.  Enter the first task (or resource).
     2.  Press "F5" (or "F7") to record it and clear the frame.
     3.  Press "Enter" to re-select the last one recorded.
     4.  Press "Home" and modify the name.
     5.  Press "Enter" to select the new task/resource.
     6.  Modify the data (rather than re-key it) as required.
     7.  Repeat from step 2 until done.

     Solution 2:  Is  accomplished  by using the  .SKB command file and  an
     editor program to build it. Some editors allow block copies and global
     changes. Refer to the appendix which defines command files.

     The initial data should look as follows:

         "\.\0?"    This will get you to the F5 frame.

             "\." Gives the background a chance to start.
             "\0?" Selects F5.
             Note: Do not enter the quotes.

         "\0A"     Gets you to the F7 frame.

     You can use the "Alt Number" keyboard function to enter extended ASCII
     codes. These codes  can be  found in  the BASIC Manual Appendix  which
     describes extended codes that have a null as the first character.

     The "\0"  command  provides  the null and the ASCII code for F5 can be
     entered  by using "Alt,6,3" or  by entering the  equivalent  character
     "?".

     Solution 3:  The ".SKB"  file  used for solution 2  can  be created by
     writing a  program  in  BASIC  or  some other language. This might  be
     appropriate if the data  is already  in  existence in some other form.
     For example a list of resources or names.

     This technique would provide automated maintenances of  the data since
     the process could be repeated when the source was changed.




     HITT Personal Software          Page 45





                                    SCHEDULE



     CREATING CALENDARS


     If  you intend to create a large number of calendars or a calendar for
     extended periods it may be easier to create a command file that can be
     reused after minor modifications with an editor.

     Refer to the COMMAND Appendix for an explanation of the commands.



     DATA BASE MAINTENANCE


     Normal  data base maintenance should  be preformed  as described using
     the  "D" function on  the  F10 frame.  This  insures that records  are
     deleted  at appropriate times  so  that continuous  scheduling  is not
     adversely effected.

     There is an alternate method which applies in some circumstances using
     the Ctl" key  in  conjunction with "Pg Up", "Pg Dn",  and "End"  keys.
     There are cautions however with using this method.

     Individual records  can  be deleted from the Job, Task, Resource,  and
     Calendar data bases (x.JOB, x.TSK,  x.RES, and x.CAL) by selecting the
     record  on  the appropriate frame (F3,  F5, F7,  F9) and  holding  the
     "Ctl" key while pressing the "End" key. The record will be deleted and
     the  next record  in  the  data base displayed. *Caution* Holding down
     "Ctl,End" will delete multiple records at a type-o-matic rate.

     Once a record is selected (whether or not you  intend to delete it) it
     is possible to step through the data base records by pressing "Ctl, Pg
     Up"  or "Ctl, Pg  Dn". This is required when deleting TASK DESCRIPTION
     records which have  more than one record associated with it (NUMBER OF
     RECORDS > 1). It is essential that you find and delete all the records
     associated with the task name.

     **CAUTION**  Deleting records using the "Ctl,End" function should only
     be done  when there is  nothing being processed in the background  and
     there are no jobs partially completed.



     SORTING THE DATA BASE


     You  can only  sort the  data  base  when there are no incomplete jobs
     since the checkpointed tables refer to records in the data base by the
     record  numbers, and these numbers  will change  when the data base is
     sorted. If the project  has  been  started  (the  first task  has been
     marked  as having started) you must  copy the  files to  a new project
     name and use this procedure on the temporary project data.

     DOS 2.x and above comes  with a SORT and  FIND filter that can be used


     HITT Personal Software          Page 46





                                    SCHEDULE



     to  sort  the .JOB,  .TSK, .RES, and the .CAL files. The DOS SORT only
     works for files less the 60,000 bytes so watch your file size and keep
     a backup copy of your  data base.  If  your files get larger that this
     you will need one of the other sort programs available on  the market.
     Use the  following commands where  %1 equals the project name. This is
     in a form appropriate for a batch (BAT) file.


         SORT <%1.JOB >%1.TMP
         FIND ":" <%1.TMP >%1.JOB
         SORT <%1.TSK >%1.TMP
         FIND ":" <%1.TMP >%1.TSK
         SORT <%1.RES >%1.TMP
         FIND ":" <%1.TMP >%1.RES
         SORT <%1.CAL >%1.TMP
         FIND ":" <%1.TMP >%1.CAL
         ERASE %1.TMP

     The  FIND filter  is  required  to eliminate a null  record  which  is
     somehow created by the SORT filter.

     These files are standard ASCII files and can be  edited  with standard
     editors. Care must be  taken to maintain  the  record length  and  tab
     substitution is not allowed.  The other files  used by SCHEDULE (.STA,
     .ACT, .TMP) are binary files and will probably be destroyed by editors
     that expect ASCII files.

     The  .TSK  file  has some special considerations.  The records contain
     numbers which  are  record  number pointers to  the previous extension
     record.

     After the sort is completed it  will be  necessary  to  reconnect  the
     extension records in the .TSK data file. This can be accomplished with
     the following manual procedure.

     1.  Start the SCHEDULE program with the sorted data base.
     2.  Press F5 then enter to select the first record.
     3.  Press F5 repeatedly until no more extensions appear.
     4.  Press enter to re-select the record.
     5.  Press Ctl-PgDn until you get to the next 1st of N records
     6.  Repeat from step 3 until there are no more records.

     The above procedure will reconnect the record extension pointers. This
     procedure can be described in a command file.



     RESOLVING MULTIPLE ACTION REQUIRED MESSAGES


     While developing a new  project data  base  it  is  not unusual to get
     multiple messages about unresolved names or calendar codes.

     The normal process for resolving these discrepancies is  to start with


     HITT Personal Software          Page 47





                                    SCHEDULE



     the last one first  (it's  the  one  still being  displayed  when  the
     scheduling has completed). Then  to reschedule again and  work on  the
     next message.

     In  some cases  it may  be  more convenient  to  look  at some  of the
     internal tables  developed by  the  program  to  assist  in  resolving
     multiple messages without having to reschedule each time.

     "Ctl,F1" displays the  main matrix task grid. If you  have printed the
     data base it will help you decode the  numeric substitute numbers such
     as JOB, TASK, and  RESOURCE, since these are the record numbers listed
     by the file print functions.



     TASK "     " NOT FOUND FOR JOB "    "


     This  message will appear when  a JOB specifies a TASK which is not in
     the data base or  when a TASK specifies another TASK as a prerequisite
     which is not in the  data  base.  The "Ctl,F1"  table  will  have  the
     unresolved task names  displayed  on the right side just  proceeding a
     status code of 1. You  will find all the unresolved  task names listed
     in this table.

     With a working  task description data base  the  message will normally
     indicate a  typographical error  in the JOB definition  record  and is
     easily located. With  an incorrect task prerequisite however it is not
     always obvious.

     The  task  associated with the mismatched  name can be  determined  by
     using the  ONODE  number.  If  the  ONODE  is 0000  it is the job name
     specified which is requesting  the task which cannot be found.  If the
     ONODE is non-zero find the entry with an equal INODE number. The  task
     number  specified in this entry is the task specifying  a prerequisite
     task name which  cannot  be  matched. Find  this  task using the  task
     number and a task file listing.



     CALENDAR " " NOT FOUND FOR RESOURCE " "


     If the  calendar code is correct and the  calendar  does  exist  it is
     possible that one  of the other  possibilities  listed in  the message
     section applies.

     "Ctl,F4" will display all  the calendars found  in the data base which
     are  associated with resources required for  the  set  of  tasks being
     scheduled.  You  can  determine  the  Years,  and  Months,  which  are
     available without requiring a calendar file listing.

     "Ctl,F3"  will  display  all  the  resources associated with the tasks
     being  scheduled. Only the Generic  name is directly available but the


     HITT Personal Software          Page 48





                                    SCHEDULE



     resource number is the  record number. The tasks  which are attempting
     to schedule the resource can be found in the "Ctl,F2" table.



     RESOURCE "" IS NOT AVAILABLE FOR TASK ""


     "Ctl,F2"  will display the resource names required for  each task.  If
     you look  down  the  FLAG column  any FLAG=0 is an unresolved resource
     name.



     REDEFINING THE KEYBOARD


     The "SCHEDULE" program does not provide any facilities for  redefining
     the keyboard keys directly.

     If  you are using DOS  2.x there is  an "EXTENDED SCREEN  and KEYBOARD
     CONTROL"  facility  that  can be used for that  purpose. See  your DOS
     manual.

     To  use this  facility  you must  include  "DEVICE=ANSI.SYS"  in  your
     "CONFIG.SYS" file. You can  then use an editor to create  a file  with
     the appropriate controls and then use the "TYPE" command to effect the
     keyboard changes.

     Since  the changes will be in effect for DOS  as well as for  SCHEDULE
     you will need to create a second set of redefinition controls  to undo
     the changes when you are done using SCHEDULE.

     This can all then be  placed in a .BAT file  to provide single command
     execution.  The command "SCHED  project" will effect the  change using
     the following files.

         SCHED.BAT

             TYPE change.kbd
             SCHEDULE %1
             TYPE undo.kbd

         CHANGE.KBD

             -[0;25;"Poughkeepsie, N.Y."p

         UNDO.KBD

             -[0;25;0;25p

     The above  will  cause "Poughkeepsie,  N.Y."  to  be  entered  anytime
     "ALT-P" is pressed. This process can  be used  to setup macro's  as in
     the  example or to redefine any of the keys. The  number of characters


     HITT Personal Software          Page 49





                                    SCHEDULE



     that can be translated is limited by the table size in this facility.

     NOTE:  In the above example the  "-" character  is  an "Esc" character
     which normally displays as an arrow pointing left.



     HEADER LINE PRINTING


     Frame 10  allows you  to enter a line to be printed as the header line
     of all listings  (F10 "H"). This facility can be used in  a number  of
     ways  since  it  allows  entry of any  keyboard  character (Null first
     extended codes cannot be entered).

     Most commands to the printer  can be issued from this line entry. Esc,
     Enter, Tab, and all other ASCII keys (Line feed) can  be entered  into
     this line. The following are ideas which consider this capability:

     Tired ribbons:  The  life of old ribbons can  be prolonged by printing
     twice  over each line. The  printer  will print at less  than 1/2  the
     speed. Double print is a command which  is not used by the program but
     can be invoked by entering the command on the "H" line.

         Enter "Esc G" to turn on Double Print. ("Esc H to turn it off)

     Multiple  header  lines:  Since the  carriage  return  and  line  feed
     characters  can be  entered  the  header  can  occupy  multiple  lines
     (limited  to a total  of 78 characters). You must reduce the number of
     lines per  page  specified in order to compensate for  the  number  of
     lines over one.  Also you  can  use the  TAB character to position the
     header line without using up the entry line space with blanks.

     Header  line control  characters:  The header  line  can be printed in
     Condensed, Underscored,  Emphasized, Double  strike, etc. by  entering
     the   appropriate   control   characters.  Some  of   these   will  be
     automatically reset, others will not.

     The following printer commands are  reset by the program after the "H"
     line has printed.

     o   Double Width
     o   Compressed Character mode
     o   Page length (will be set according to the F10 frame)

     Changing  the header for each page:  Since the  printing is being done
     in the background  and  the  header  line entry  is being  done in the
     foreground it is  possible to change  the line  as printing  is  being
     done.  You can suspend the  printing by making  the printer  not ready
     (Press on-line button) while you  are changing the header line for the
     next page. Do not turn the printer  power off  as that would reset all
     the special controls.




     HITT Personal Software          Page 50





                                    SCHEDULE



     CHAPTER 16. SCHEDULE TRAPS



     This  chapter is  the  place  I have documented the traps  people have
     gotten into. Read over the list  and avoid the  problems. If all  else
     fails ask for Don (Hitt) at HITT Personal Software.



     RESOURCE NAMES


     Many  resources may have the same generic name. A generic name  cannot
     be  the same as a specific  name  of a resource. The program does  not
     check for this duplication and may allocate the wrong resource.



     HOURS/DAY FIELD IN THE TASK DESCRIPTIONS.


     This  field should be left blank if the task also  specifie a resource
     that  uses a calendar. Using  both (resource  calendar and HR/DY) will
     cause a problem because the program  will try to  use  the task  HR/DY
     field  to  create  its  own calendar  from  hour zero  to  the  number
     specified. See the chapter on PROJECT PLANNING for the appropriate use
     of this field.



     CREATING GANTT FILES.


     If you  set the lines/page  option of  SCHEDULE  frame F10 to zero the
     printer control  characters will be suppressed  and  the  program will
     assume a continuous form. That is  the correct form  for GANTT. I like
     print option 2 and 6*** for my GANTT  charts. Direct  the print to the
     disk using the "O" option.

     There is a batch and  command file on the  SCHEDULE diskette that will
     automatically link the programs. Look for the following files:

     o   PLAN.BAT

     o   PLAN.SKB

     o   VIEW.BAT

     o   VIEW.GKB

     You may need  to  modify this  file for  your system configuration and
     disk structure.



     HITT Personal Software          Page 51





                                    SCHEDULE



     SCHEDULING LATE AND CALENDAR NOT FOUND MESSAGES


     If you use AM, PM time in the  calendar definition rather than 24 hour
     time it may look to the program as though the time is going backwards.
     You must use 24 hour time (00:00 to 24:00).

     The program does  not check for  this condition  and will not schedule
     any time for the backward periods. It  therefor runs out  of calendars
     and gives the no calendar message.



     EDITING THE DATA BASE


     The project.JOB, project.TSK,  project.RES,  and project.CAL files are
     ASCII  and  can  be edited  with most editors.  The record length must
     remain fixed.

     Don't use an  editor on the project.STA  or project.ACT  files as they
     are binary.

     o   project.STA is the checkpoint file for restarting the program.
     o   project.ACT  is  an extension  of the checkpoint and contains  the
         last scheduled resource activities.

     Always store the files with the NO TABS option.

     If  you move data  around, read the expert chapter abo7ut  sorting the
     data base. The project.TSK file has special considerations.

     The  program deletes records by placing a blank  in the first location
     of  the appropriate  record(s).  New records are placed in the deleted
     locations, or if none, at  the end of the  file. This process  retains
     the  name to  physical  location  relationship required  once you have
     started the project.

     The project.TSK file has backward pointers to connect multiple  record
     task description records. Use the RECONN.KBD command file to reconnect
     these records if you have moved them around.















     HITT Personal Software          Page 52





                                    SCHEDULE



     CHAPTER 17.  COMMAND FILE



     When SCHEDULE  is invoked it attempts  to  open  a disk file to use as
     keyboard  input. The  file has the same  first file name (the  project
     name) as the remainder of the files and the extension of "SKB". If the
     file is not present on the same disk as the data base the program will
     use the normal keyboard.

     Each character  is  used by  the  programs  as  if  it came  from  the
     keyboard. In addition the "\" (back slash)  is  used to indicate  that
     the next character is a command rather than a keyboard character. This
     technique is used to  provide the  demonstration sessions and can also
     be used to  predefine a particular setup or to  drive the program much
     like "PIPING" (a DOS 2.+ function).



     COMMAND DEFINITIONS


     \.  Pause 1 second:  Wait for  the next second timer tic. This command
     can be used to provide delays. The background will continue during the
     delays. It is sometimes used in conjunction  with the  "\," command to
     insure  that  the next  printout  has  an  opertunity to start  before
     looking for completion with the comma command.

     \, Wait for processing or any key:  Wait  for background processing to
     complete or for  any key  to be depressed. The  keyboard option allows
     for problems, such as the printer not being ready, which could prevent
     the background from ever completing.

     \
      Comment.:  All characters on the line after this code are passed over
     and not  used. This  allows comments to be placed in the command file.
     In  addition  it can be used to prevent the carriage  return code from
     being passed to the program  [see Carriage  return  (13)]. Comments do
     require  time  to  pass  over  during  the  execution of the  keyboard
     procedure and therefor should be placed after procedures that loop.

     \Bx Branch to \Nx:  This command resets the command file and  scans it
     to  find the  position named x as defined  by the \Nx command. Command
     processing  is  then  restarted  with  the character following the \Nx
     command. If a matching  \Nx is not found, control is  returned  to the
     keyboard.  The   branch  can  be  made  conditional  by  using  it  in
     conjunction with the \U or \E commands on the same line.

     \C Clear the  display:  Clear  the selected display screen and set the
     locate address to zero.

     \D Display:  The characters following this command are directed to the
     selected display starting at the locate address. The locate address is
     updated +1 with each character.


     HITT Personal Software          Page 53





                                    SCHEDULE



     The display mode is terminated with the next command  (\).  When using
     the  graphics display as the  80 character/line display it is selected
     as the monochrome display and the \G selection is disabled.

     This display does not affect the cursor position or  display  pointers
     being used by SCHEDULE.

     \Ex  If  Equal:  If the character x is equal to the  monochrome screen
     character pointed  to by the locate address,  Do  the remainder of the
     line. Else skip the remainder of the line (to the next ASCII 13).

     \G Select the Graphics 40x25:  Select the graphics display (TV). 40x25
     (This is the default selection)

     \Lnnnn Locate:  Locate the display and conditional test pointer to the
     screen  character position  nnnn where 0000=Top left  and  1999=Bottom
     Right of the  80  character per line display  and 0999=Bottom Right of
     the 40 character per line display.

     \M Select the  Monochrome 80x25:  Select the display being used as the
     80x25 (This may be the graphics display if it  is being used as the 80
     character display.)

     \Nx Name  this position x:  This is  used in  conjunction with the  \B
     command  to allow  looping within the keyboard procedure. The position
     of the \Nx marks the  target of the \Bx. (x is any  character and must
     match the x in the \Bx.)

     \Ux If Unequal:  If the  character x  is not equal  to the  monochrome
     screen character pointed to by the locate address, do the remainder of
     the line. Else skip the remainder of the line (to the next ASCII 13).

     \W  Wait for any key:  Wait for any key to  be depressed. Used to pace
     the demonstration to the user speed. The key actually depressed is not
     used.

     \X  Exit  to the keyboard:  Keyboard entry is allowed  at this  point.
     When "Esc" is pressed control  is returned to the  command file at the
     point following this command.

     \0x ZERO:  Enters  a null.  This allows you to enter special  keyboard
     characters  not  normally allowed by  editors. See  your Basic  Manual
     (Appendixes  G) for  a  definition  of the null-x  extended  character
     codes. These  codes  are  used to stimulate functions such as function
     keys or cursor controls.











     HITT Personal Software          Page 54





                                    SCHEDULE



     ADDITIONAL CONTROL


     In  addition to the "\" command  characters,  the carriage return (13)
     character is handled as follows.

     Carriage return (13):  This code is normally inserted  at  the end  of
     each line by editor programs. It  is then followed  with a  "Line feed
     (10)" code.

     The carriage return is used as follows:

     o   If  in display  mode the  display pointer is advanced to the  next
         40th position. This forces the display pointer to  the  next  line
         (or half line on the monochrome display). The line feed characters
         are skipped.

     o   If in keyboard input mode  an "ENTER" key is passed to the program
         and the next character (normally a line feed) is skipped.

     o   If directly following a "\" the carriage return is skipped and the
         character  following is  passed to the program (normally  the line
         feed ASCII 10).

     o   If following a  "\;" anywhere on the line the carriage return  and
         the character following (normally a line feed 10) is skipped.






























     HITT Personal Software          Page 55





                                    SCHEDULE



     CHAPTER 18. PROGRAM EXIT RETURN CODES TO DOS



     IBM DOS 2.0 and above supports the ability of a program to set an exit
     code  that can be interrogated from a batch file  (.BAT) using the "IF
     [NOT] ERRORLEVEL  n"  DOS  command.  DOS  1.1  does  not support  this
     command.  Refer to  your  DOS manual  under BATCH  PROCESSING for  the
     command definition.

     SCHEDULE attempts to set this code as it terminates (exits to DOS). If
     the attempt fails  it  then exits with DOS  1.x  conventions  (no exit
     code).

     The codes set by SCHEDULE are as follows:

         0 = Normal exit via the Esc key.

             The checkpoint was successful.
             Background processing had completed.

         1  =  Exit  was  by  the Esc key and  a  "Y" response to the  busy
         message.

             The checkpoint  was  successful  but depends on the  state  of
             processing.
             Background processing was terminated.

         2 = Exit was by the Ctl F10 key (A debug mode exit).

             No checkpoint was taken but all files were closed.
             The background processing state is unknown.

         4 = Exit was via the Esc Key.

             The  checkpoint  attempt  did  not have enough  disk  space to
             complete.
             Background processing had completed.

         5  =  Exit was by the  Esc key  and a  "Y"  response  to the  busy
         message.

             The checkpoint attempt did not have enough disk space.
             Background processing had not completed.

         6 = During start up it was not possible to open the  required data
         files. The program also attempted and failed to  create  the  data
         files.

             This is normally caused by the  disk  file  index  space being
             full.

         8  = There was  not  enough processor storage to support the  data
         area required.


     HITT Personal Software          Page 56





                                    SCHEDULE



     As with most return codes the  number  increases with the severity  of
     the  problem.  When  multiple conditions  occur  the highest  code  is
     indicated.

     The  batch file "EXITCODE.BAT" will display  the meaning of  the exits
     and can be used  by other batch files by branching on  the error level
     of concern to this file.

     For example:

     "IF ERRORLEVEL 1 EXITCODE" placed in a batch file will exit that batch
     file, if it  is a  1 or greater, and  will display  the meaning of the
     exit code.











































     HITT Personal Software          Page 57





                                    SCHEDULE



     APPENDIX A. MESSAGES



     ACTIVITY FILE DISK FULL:  Activity recording has been terminated prior
     to the count allowed on the control frame (F10) because the  disk  has
     run out of space.

     Scheduling will continue with this reduced activity count. See the MAX
     ACTIVITIES parameter setting on frame "F10" and the description of the
     considerations for this setting in the F10 control frame description.

     Do not attempt  to exit the program at this point as additional  space
     may be required to take the check point and you may  loose the started
     and completed task status.

     Make the MAXIMUM ACTIVITIES smaller than the value now being displayed
     and re-schedule before attempting to exit.

     CALCULATING EST:  The schedule processing  is calculating the earliest
     start  time  for each  task.  This  is  required  after each  task  is
     scheduled if the task was delayed because of resource constraints.

     CALCULATING  LST:  The schedule  processing  is calculating the latest
     start time for each task. This always follows CALCULATING EST.

     CALENDAR  "  "  NOT  FOUND FOR  RESOURCE  " ":  The  named calendar is
     required by the named task but it cannot be found in the data base.


     o   The resource calendar code may be incorrect.
     o   The calendar data base may not exist.
     o   The required month/year may not exist in the data base.
     o   A  task duration may  be incorrect which is extending the schedule
         past the last available calendar.
     o   A resource  availability time  may be extending the schedule  past
         the last available calendar.

     CAUTION do  not remove disk  "  "  before exiting this program via the
     "Esc"  key:  The  disk indicated  is being used by the program  and  a
     number  of  files  have been  opened.  Changing  the disk  could cause
     erroneous  data to be written or the catalog to be over-written unless
     the program is  terminated  via the normal  exit (Esc) before changing
     the diskette.

     When the message is removed from the screen, this is NOT an indication
     that the disk can be changed. The CAUTION is still in effect until the
     program is terminated.

     CONNECTING GRID:  The background  processing is  connecting the  input
     and output node numbers to create a critical path grid.

     ENTER  CHANGES:  Changes can be entered using the full  screen editing
     controls.


     HITT Personal Software       Appendix A-1





                                    SCHEDULE



     ENTER INFO:  Data  can  be  entered  using  the  full  screen  editing
     controls.

     ENTER NAME:  An attempt has  been made to move the cursor up from  the
     name field.

     INVALID RUN TIME IN TASK " ":  The  run time or hours per day field of
     the named task contains one of the following and should be of the form
     "Hour:minute", "Hours", or ":Minutes".


     o   Minutes greater than 59
     o   Hours per day greater than 24
     o   (note: blank hours per day =24)

     Must  be P0 to P2 or DA to DD:  Printer port 0, 1, or  2 or Disk A: B:
     C: or D: may be selected.

     Must be 0 to 3:  Day code must be 0,1,2,3, or blank (blank = 0)

     Must be 01 to 12:  Month entry is zero or greater than 12

     Must be 16  to 99:  The  page size must be in this range  or  00.  The
     printer is  set to eject to  this number of lines and will print fewer
     than this number on a page.  If 00 is entered the printer controls are
     not issued and the printout is treated as a continuous form.

     NAME FOUND:  The name entered on the first  line has been found in the
     data base and the  remainder of the  display is displaying the current
     contents of the record.

     NAME  NOT FOUND:  The name entered on the first line was not  found in
     the data base and the  remainder of the display remains  unchanged. If
     the  name is incorrect move  the cursor to the  name line and make the
     correction, otherwise this is a new data base record.

     NO STATUS FILE!:  While attempting to open all the files no "xxxx.STA"
     file was  found. xxxx = the  project  name specified when evoking  the
     program. This is a warning message which could indicate that the wrong
     disk drive is  being used  as the default drive or that the wrong disk
     has been  placed  in the drive. CAUTION: Do  not  change disks without
     exiting this program first  (Esc). The program has opened  a number of
     files  which must first  be closed  by exiting. The  message is normal
     when starting a new  scheduling session  (to start from scratch  erase
     "xxxx.STA" and "xxxx.ACT".

     OUT OF DISK  SPACE:  The disk cannot  be written because of a  lack of
     space. You must exit to DOS (Esc) and resolve the problem.

     The attempt to take a checkpoint may also fail if additional space  is
     required. If this occurs you will see a "NO STATUS FILE!" message when
     you start again, and you will be starting from scratch (in process and
     completed activity status will be lost).



     HITT Personal Software       Appendix A-2





                                    SCHEDULE



     PRINTER NOT  READY:  The  printer  is  not in  the ready  state. Press
     "Online" to make it ready.

     PRINTER  OUT OF PAPER:  The printer is  indicating  end  of forms. The
     program will continue to print to the end of the page before stopping.

     Press the "on-line" button on the printer  to take  it off-line (ready
     light off)  before putting new paper  in or the printing will start as
     soon as the end of forms indicator is gone.

     Align the paper, then press "on-line" to continue with the next page.

     PRINTER POWERED OFF:  The printer is indicating a power off condition.
     The system  will wait  indefinitely for it  to  be powered  on, unless
     terminated.

     PRINTER TERMINATING:  "T"  has been pressed on frame "F10". The system
     will complete the print line in the printer, terminate any transfer to
     the printer, drain  the buffer,  eject the forms, and reset  the print
     request.

     PROCESSING CALENDAR:  The background processing is building a table of
     the  required calendars. The  calendar definition file  "xxxx.CAL"  is
     being scanned.

     PROCESSING JOBS:  The background processing is building a table of the
     requested jobs. The  "xxxx.JOB" file is scanned to find new entries or
     modifications.

     PROCESSING  RESOURCES:  The background processing is  building a table
     of the  required resources. The resource definition file "xxxx.RES" is
     being scanned.

     PROCESSING  TASKS:  The background processing is  building  a table of
     the required  tasks  to  accomplish the  job.  The  "xxxx.TSK" file is
     scanned to find the required entries.

     RESOURCE "  "  IS  NOT AVAILABLE FOR TASK " ":  The  named resource is
     required by the named task but the allocation is not possible. Any  of
     the following is possible.


     o   The name is incorrect in the task description.
     o   The name is incorrect in the resource description
     o   The size required cannot be satisfied.
     o   The quantity required cannot be satisfied.

     RESOURCE QUANTITY NEGATIVE:  A resource quantity has gone negative. If
     tasks  are  started out  of  sequence  it is  possible  that  you have
     indicated  that a task  has been started before another  task which is
     holding a  required resource has been completed. Find  the task  which
     has been completed and mark it accordingly.

     This can also occur if the ACTIVITY file is not  in agreement with the


     HITT Personal Software       Appendix A-3





                                    SCHEDULE



     STATUS file. When  starting  over, erase the xxxx.ACT file  as well as
     the xxxx.STA file. Its also  a good idea to  check  the RESOURCE  file
     quantities  for inventory (Ixx class) and buffer (Bxx class) resources
     when starting over.

     SCHEDULE BY  JOB:  The  requested printout for SCHEDULE  BY JOB  is in
     process.

     SCHEDULING:  The schedule processing is determining the priorities  of
     the tasks and allocating resources.

     STANDBY:  This message is displayed  during  the data  base search for
     the named record.

     START/END PRINT:  An automatic print request for a job just started or
     ended is in process.

     TASK " " MUST HAVE A DURATION SINCE IT HAS A RESOURCE:  A milestone is
     a task  with zero duration  and no resources. If you assign a resource
     you must have  a  non zero  duration. A  schedule  processing loop may
     occur with this condition.

     TAKING   A  CHECKPOINT:  The  background  task  is  writing   a  table
     checkpoint to disk. This is done at the end of each scheduling run and
     also when exiting  to  DOS. This allows the  system to pickup where it
     left off without having to re-process all the information.

     TASK "  " REQUIRES A DURATION SINCE  IT HAS RESOURCES:  The named task
     is  not  a Milestone (a  task with zero time  and no resource) since a
     resource has been  specified. This  could cause  the  program  to  run
     forever in the SCHEDULING phase depending on the particular situation.
     You may eliminate  the resource  specification  or provide  a  nonzero
     duration. If the program is staying in the SCHEDULING phase, it may be
     necessary to exit the program and restart the program after fixing the
     task definition.

     THERE ARE MORE  ACTIVITIES (left side):  The table contains additional
     tasks which  should be  started.  Moving the cursor down  one past the
     last  (bottom)  entry will allow you  to see the next 5 entries. It is
     possible to see some tasks listed which were listed on previous  pages
     because of the way the table  is ordered,  but no  task will be listed
     twice on the same page.

     Moving the cursor up one position above the  top entry will return you
     to the first page.

     If  the  list  is  long  you  should  be  considering  re-running  the
     scheduling program (F10 S) unless you think it is possible to catch up
     again.

     THERE ARE MORE ACTIVITIES (right side):  The table contains additional
     tasks which should  be  completed. Up and down  cursor  controls  will
     allow you to see the additional tasks.



     HITT Personal Software       Appendix A-4





                                    SCHEDULE



     If  the list is  long  you  should consider re-running  the scheduling
     program (F10 S) unless you think it is possible to catch up again.

     THERE  IS NOT  ENOUGH MEMORY  TO  RUN SCHEDULE:  A  test of  available
     storage has been made  and there is not enough storage to  support the
     required work space. The program  will normally have enough  available
     memory on  a 128K Personal Computer using  DOS 1.1  or 2.x. If not you
     may have to  reduce the size of  DOS  by  reducing the I/O buffers  or
     other resident routines.

     TOO MANY  JOBS/TASKS SPECIFIED:  Storage  space  has  been  filled and
     compression has been unsuccessful. The background scheduling  has been
     abnormally terminated.

     It is possible that a task prerequisite loop has been created which is
     filling  the table with the same tasks or sequence  of  tasks over and
     over  again. If  so  correct  the  task  prerequisite  definition  and
     re-schedule.

     Although storage requirements are a function of many factors it should
     be possible to contain in excess of 1000 tasks at a time.

     If you have not created a loop,  you have exceeded the capacity of the
     system.  The  project  must  be  broken  into  multiple  projects  and
     interdependences must be manually controlled.

     UNDEFINED TASK NAME " " FOR JOB " ":  Either the job named by FOR  JOB
     is  requesting an  incorrect task  name  or a task  description has an
     incorrect prerequisite name  in the string of tasks  required for  the
     named job.

     When developing task descriptions it is sometimes helpful to allow the
     system  to find  these undefined tasks  as  one  builds  the data base
     starting  from  the  requested end result. In these  cases the message
     will lead you through the definition process by using a test case.

     VIEW  ONLY:  The  data  base  cannot  be modified unless it  is  first
     unlocked using  the  F10 U  control. Locking  the data  base  prevents
     accidental  modifications. xxxx.TSK, and  xxxx.RES  are controlled  by
     this switch.

     WAITING  FOR PROCESSING:  The  requested  display  cannot be  provided
     because the  table that is  required to resolve  prerequisite and task
     start/stop status is being changed.

     If  you  have  the  2nd  display  option, try  using  the  F4, F6, F8,
     functions to get the data you need.









     HITT Personal Software       Appendix A-5





                                    SCHEDULE



     APPENDIX B. SERVICE PROJECT ENVIRONMENT AND DATA BASE



     The  sample  data  base  describes  a  fictitious  automotive  SERVICE
     STATION.

     Our  service  station  has  four  people resources  all  of  them  are
     described by the generic name MECHANIC.

     OLD  TIMER  is the main  mechanic.   He  can perform  any job  and  is
     licensed to give automotive inspection stickers.

     JACK BE  NIMBLE  is the  apprentice and  helper. He can do some of the
     mechanic type work but is not qualified in most areas.

     EXTRA HELP is available  sometimes.  When he  is, we  set the quantity
     field and availability time accordingly. EXTRA HELP is qualified to do
     mechanic work but is not licensed to give inspections.

     BOSS is also a  qualified mechanic but steps in only  when  a  job  is
     going to be late.

     OLD TIMER and BOSS go to lunch together. They both use calendar "A" to
     describe their availability hours.

     JACK  BE NIMBLE and EXTRA HELP have a shorter lunch break but  come to
     work later. Also,  they  have to watch  the store until the  BOSS gets
     back. They both use calendar "B" to describe their availability hours.

     The station has 3 (generic name) WORK AREA's.  Two racks and space for
     one additional car.

     At FLOOR SPACE 1 we can do work that does  not require a rack, this is
     where the wall is marked for headlight adjustments.

     RACK A and  RACK B can be used interchangeably except that only RACK A
     has access to the grease gun.

     A lot  next to the  station  will hold more  cars than  necessary. The
     station will hold a total of 3 (buffer class resource BLD).

     Some tools can create  conflicts because they may be required  at more
     than  one place at a time. We will  define them as resources  so  this
     conflict  can  be  resolved.  TIMING   LIGHT,  TIRE  TREADGAUGE,  LAMP
     ALIGNGAUGE are of this type.

     Normally used inventory items will also be tracked. Cases of OIL  come
     in  once   a  month.  OIL  10W-40  GRPx  is  added  with   appropriate
     availability  dates as they are ordered.  SPARK PLUGS, AIR FILTER, OIL
     FILTER and GREASE will only be tracked by there totals (not by type).

     The  station  offers normal automotive  maintenance. Customers can ask
     for a variety of jobs. Most of the jobs are normal everyday items that


     HITT Personal Software       Appendix B-1





                                    SCHEDULE



     we  can specify  in  the task  data base. Jobs  like TUNE UP, SERVICE,
     INSPECTION, LUB, OIL, AIR FILTER, ANNUAL, and BREAK CHECK  are defined
     as a model  of task  descriptions. These  models can  be used  by many
     customers  since  they  will be operating on  different JOB  resources
     (CUSTOMER CAR).

     As  customers  come to the station or call  for  appointments we  will
     select F3 and enter  the  names of  the  jobs they would like done. In
     addition we enter the  date and time they can make there car available
     and the time they would like to have it back.

     If  a  special  or unusual  job  is requested we will ask the boss  to
     estimate the task and create a new task description model.

     Sometimes our first assumptions are found to be incorrect.  If we find
     that  the brakes don't pass  inspection we  can dynamically change the
     requested job to include BRAKE PADS and reschedule.

     When the customer  calls and asks  for the  status of his job. We will
     enter  his name (F3) and display the status (F6) for his job. When the
     job  is completed we will automatically get a printout of  the  actual
     start and ending times of each task.

     On frame F10  we will probably want  print  request 4  and 5 on,  AUTO
     START  on,  and  DATA  BASE  MAINTENANCE  on.  This  will  normally do
     everything we need without having to refer to this frame.

     Normal operation will be to monitor the F2 frame and use  the 25 by 40
     monitors to display the detail to the mechanics as they start the next
     task.  We will mark task actual  start and  ending times with  an X on
     this (F2) frame.

     The  forgoing   describes  a  fictitious  environment  that  has  been
     described to  SCHEDULE as a SERVICE  project data base.  The resources
     and tasks can be displayed and you can make up customers with requests
     to observe the operation.




















     HITT Personal Software       Appendix B-2









INDEX



     A                               CPM  1, 2, 3
                                     Critical Path  4, 39, 40, 41
Abstract  3                          Cursor controls  13
ACT file  47
Activities  3, 4
Activity display  21                      D
Adapters  45
Alt Number  45                       DAA  43
AON Activity on node  3              Data base  6, 7, 12, 15, 18,
Arrow Diagrams  3                       20, 25, 27, 45, 46, 47
ASCII  47                            Data base listing  24
Auto processing  24                  Data base maintenance  25
Aux monitor  11                      Date time display  11
                                     Decisions  5
                                     Delete  12, 46
     B                               Delete a TASK  16, 25
                                     Deleting records  25
Background  3, 10                    Development Projects  36
Background display  11               Disk files  8
Backup the program  2, 9             Disk space  26
Basic  45                            Display  8, 55
Batch  44                            Display Command  53
Batch files  32, 35                  Display format  11
Bottom Up Plan  36                   DOS  8, 56
Brackets  12                         Dummy Tasks  3
Branch Command  53
Buffer resource  5, 20, 27
                                          E

     C                               Early display  24
                                     Edit  6
Calculating EST  7                   Edit controls  13
Calculating LST  7                   Edit conventions  12
Calendar  4, 5, 6, 11, 18, 42,       Editing files  52
   46                                End Key  46
CALENDAR NOT FOUND  52               Ending tasks  20
Capital Resources  4                 Equal Command  54
Carrage Return  55                   Erase records  25
Clear Command  53                    Esc key  10
Colons :  12                         Events  3
Color control  25                    Exit command  54
Command  44, 45, 46, 47, 50,         Expert  44
   53                                Expert Friendliness  1
Command file  32, 35
Comment Command  53
Concepts  7                               F
Connecting grid  7
Control  23                          File  45, 53
Control field  12                    Find  47
Copying the program  2, 9            Foreground  3, 10


                                                                 Index-1









Frame 10 controls  32                License  2
Full screen edit  13                 Limitations of use  2
Function keys  10                    Line Feed  55
                                     Locate Command  54

     G
                                          M
GANTT files  51
Generic name  27, 28                 MAP  2
Generic Resources  5                 Meeting calendar  33, 34
Getting started  9                   Message  47, 56, 57
Graphics Command  54                 Mile-Stone  3, 36, 39
Grid  6                              Models  3, 6
                                     Monochrome Command  54
                                     Multiple jobs  6
     H

Header  50                                N
Header print line  24
Help  1, 10                          Name command  53, 54
Hints  44                            Network  6
Hours                                Null Command  54
    Day  51

                                          O
     I
                                     Organization  39
Ideas  44                            Output selections  11
If Not Errorlevel  56                Overlap  6
Insert  12
Interactive display  11, 21
Inventory resource  5, 20, 27             P

                                     Pause Command  53
     J                               PERT  1, 2, 3
                                     Pg Dn Key  46
Job  3, 11, 30, 31, 37, 39, 41       Pg Up Key  46
Job description  15, 33              Piping  53
Job file  32                         Precedence method  3
Job resource  5, 28                  Printer  8, 44
Job status display  21               Printer selections  23
                                     Problems  51
                                     Process controls  11
     K                               Processing calendars  7
                                     Processing Jobs  7
Keyboard  49                         Processing resources  7
                                     Processing tasks  7
                                     Program operation  10
     L                               Project  3
                                     Project Management  43
Labor Resources  5                   Project Planning  2, 36





                                                                 Index-2









     Q                                    T

Quality  36, 41, 42                  Tab  47, 50
                                     Tables  6
                                     Task  3, 4, 11, 28, 31, 37,
     R                                  40, 41
                                     Task description  16, 33
Record deletion  25                  Task detail display  21
Record selection  12                 Task Duration  37, 38
Redirect  49                         Task Model  3
RES file  20                         Tasks  7
Reset print requests  24             Terminal Emulation  45
Resource  2, 3, 4, 6, 7, 11,         Terminating printing  24
   27, 31, 37, 38, 40, 41, 42        Time  4, 7
Resource description  17, 34         Time date display  11
Resource names  51                   Time stamp  30
Ribbons  50                          TMP file  47
RS-232  44                           Top Down Design  36
                                     Tracking  30
                                     Transfer the program  2
     S                               Traps  51
                                     TSK  47
Schedule  2, 7, 41                   Tutor  27, 29
Security header  24
Sequence  7
SKB  53                                   U
Slashes   12
Smoothing  41                        Unequal Command  54
Sort  32, 46, 47                     Updating data  13
Specific Resources  40
STA file  20, 47
Staff assignments  30                     W
Start processing  24
Starting tasks  20                   Wait command  53, 54
STATION  10, 18                      Warranty  2
Status display  11
Storage size  8
System requirements  8                    Z

                                     Zero Command  54
















                                                                 Index-3